## ACL_Oct_2023
October 2023 ISO-NEW ENGLAND Asset Condition Update - ISO-NE Public
Primary Driver | Section # | Asset Condition ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Asset Condition Grouping | Description | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Jun-20 Status | Oct-20 Status | Mar-21 Status | Jun-21 Status | Oct-21 Status | Mar-22 Status | Jun-22 Status | Oct-22 Status | Mar-23 Status | Jun-23 Status | Oct-23 Status | PPA (I.3.9) Approval | TCA Approval | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs | Jun-20 Estimated PTF Costs | Oct-20 Estimated PTF Costs | Mar-21 Estimated PTF Costs | Jun-21 Estimated PTF Costs | Oct-21 Estimated PTF Costs | Mar-22 Estimated PTF Costs | Jun-22 Estimated PTF Costs | Oct-22 Estimated PTF Costs | Mar-23 Estimated PTF Costs | Jun-23 Estimated PTF Costs | Oct-23 Estimated PTF Costs
Table A
Maine
New Hampshire
Asset Condition | 1a | 280 | NH | Eversource |  |  | 2023-12-11 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - E115 Line | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2021-07-15 | 2023-05-31 | [15 empty] | 55116000 | 55116000 | 55116000 | 55116000 | 55116000 | 64147000 | 64147000 | 64147000 | 64147000
Asset Condition | 1a | 281 | NH | Eversource |  |  | 2024-06-01 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - Z180 Line | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | 2021-07-15 | 2023-05-31 | [15 empty] | 9669000 | 9669000 | 9669000 | 9669000 | 9669000 | 9669000 | 14529000 | 14529000 | 14529000
Asset Condition | 1a | 308 | NH | National Grid, USA |  |  | 2027-12-01 |  | Moore #20 Substation Asset Condition and Separation | [18 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | 2022-12-14 | No | [18 empty] | 49307000 | 49307000 | 49307000 | 49307000 | 49307000 | 49307000
Asset Condition | 1a | 343 | NH | Eversource |  |  | 2024-06-01 |  | Timber Swamp Station 345 kV Breaker Replacements | [20 empty] | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [20 empty] | 7431000 | 7431000 | 7431000 | 7431000
Asset Condition | 1a | 349 | NH | Eversource |  |  | 2025-06-01 |  | Scobie Pond Station 345 kV Trench Replacement & Control House Expansion Project | [20 empty] | Proposed | Under Construction | Under Construction | Under Construction | NR | 2023-04-25 | [20 empty] | 19652000 | 19652000 | 19652000 | 19652000
Asset Condition | 1a | 351 | NH | Eversource |  |  | 2024-12-01 |  | Greggs Substation Rebuild | [21 empty] | Under Construction | Under Construction | Under Construction | 2022-11-16 | 2023-09-12 | [21 empty] | 72193000 | 72193000 | 72193000
Asset Condition | 1a | 367 | NH | Eversource |  |  | 2023-12-01 |  | 115 kV Structure Replacements and OPGW Installation - P106 Line | [21 empty] | Under Construction | Under Construction | Under Construction | NR | 2023-07-27 | [21 empty] | 5634000 | 5634000 | 5634000
Asset Condition | 1a | 368 | NH | Eversource |  |  | 2023-11-01 |  | 115 kV Structure Replacements and OPGW Installation - Q171 Line | [21 empty] | Under Construction | Under Construction | Under Construction | NR | 2023-07-27 | [21 empty] | 14966000 | 14966000 | 14966000
Asset Condition | 1a | 370 | NH | Eversource |  |  | 2024-03-01 |  | Line 381/379 Optical Ground Wire Upgrade | [21 empty] | Under Construction | Under Construction | Under Construction | NR | No | [21 empty] | 8238000 | 8238000 | 8238000
Asset Condition | 1a | 380 | NH | Eversource |  |  | 2023-12-01 |  | NH Asset Condition Project - H123 Line | [22 empty] | Under Construction | Under Construction | NR | No | [22 empty] | 5800000 | 5800000
Asset Condition | 1a | 386 | NH | Eversource |  |  | 2024-12-01 |  | Northern New Hampshire 115kV Line Rebuilds - B112 Line | [22 empty] | Proposed | Under Construction | 2023-06-14 | No | [22 empty] | 105430000 | 105432000
Asset Condition | 1a | 394 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - E194 Line | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 8670000 | 8670000
Asset Condition | 1a | 395 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - U181 Line | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 8510000 | 8510000
Asset Condition | 1a | 397 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - 307 Line | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 9420000 | 9417000
Asset Condition | 1a | 399 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - J114 Line | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 9710000 | 9709000
Asset Condition | 1a | 401 | NH | Eversource |  |  | 2024-03-01 |  | Laminated Wood Structure Replacement Program Phase III - C189 | [23 empty] | Under Construction | NR | No | [23 empty] | 12808000
Asset Condition | 1a | 402 | NH | Eversource |  |  | 2024-03-01 |  | Laminated Wood Structure Replacement Program Phase III - H137 | [23 empty] | Under Construction | NR | No | [23 empty] | 7788000
Asset Condition | 1a | 405 | NH | Eversource |  |  | 2024-03-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - H141 | [23 empty] | Under Construction | NR | No | [23 empty] | 18750000
Vermont
Asset Condition | 1a | 232 | VT | Vermont Electric Power Company |  |  | 2025-12-01 |  | Line 340 Asset Condition Structure Refurbishment | [13 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [13 empty] | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000
Asset Condition | 1a | 235 | VT | National Grid, USA |  |  | 2025-07-01 |  | Vernon #13 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | 2022-07-20 | No | [19 empty] | 39690000 | 39690000 | 39690000 | 39690000 | 39690000
Asset Condition | 1a | 284 | VT | Vermont Electric Power Company |  |  | 2025-12-01 |  | Line K24 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-20 | [15 empty] | 15240000 | 15240000 | 15240000 | 15240000 | 15240000 | 15240000 | 15240000 | 15240000 | 15240000
Asset Condition | 1a | 305 | VT | Vermont Electric Power Company |  |  | 2026-12-01 |  | Line K42 Asset Condition Line Replacement | [18 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | 2022-03-17 | No | [18 empty] | 49000000 | 49000000 | 49000000 | 49000000 | 49000000 | 49000000
Asset Condition | 1a | 330 | VT | Vermont Electric Power Company |  |  | 2026-12-01 |  | Line K21 Asset Condition Structure Refurbishment | [20 empty] | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-23 | [20 empty] | 20550000 | 20550000 | 20550000 | 20550000
Asset Condition | 1a | 331 | VT | Vermont Electric Power Company |  |  | 2026-12-01 |  | Line K32 Asset Condition Structure Refurbishment | [20 empty] | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-22 | [20 empty] | 14320000 | 14320000 | 14320000 | 14320000
Asset Condition | 1a | 332 | VT | Vermont Electric Power Company |  |  | 2027-12-01 |  | Line K50 Asset Condition Structure Refurbishment | [20 empty] | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-23 | [20 empty] | 31280000 | 31280000 | 31280000 | 31280000
Asset Condition | 1a | 350 | VT | Vermont Electric Power Company |  |  | 2024-12-01 |  | Middlebury Substation Asset Condition Refurbishment | [21 empty] | Planned | Planned | Under Construction | NR | No | [21 empty] | 9000000 | 9000000 | 9000000
Asset Condition | 1a | 383 | VT | Vermont Electric Power Company |  |  | 2026-12-01 |  | Line K43 Asset Condition Structure Refurbishment | [22 empty] | Planned | Under Construction | NR | No | [22 empty] | 16900000 | 16900000
Massachusetts
Asset Condition | 1a | 26 | MA | Eversource |  |  | 2023-12-01 |  | Rebuild Bourne Substation as a breaker and one half scheme |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2018-04-30 | 2021-08-21 |  |  |  | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 76000000 | 76000000 | 76000000 | 76000000 | 69893000 | 69893000 | 69893000 | 69893000 | 69893000 | 69893000 | 69893000 | 69893000
Asset Condition | 1a | 27 | MA | Eversource |  |  | 2023-12-11 |  | Kingston Substation #735 Asset Condition Replacement |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2018-04-30 | 2022-06-01 |  |  |  | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 10428000 | 10428000 | 10428000 | 10428000 | 10428000 | 10428000 | 10428000
Asset Condition | 1a | 43 | MA | Eversource |  |  | 2023-11-01 |  | K Street #385 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2018-04-17 | [5 empty] | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000
Asset Condition | 1a | 44 | MA | Eversource |  |  | 2028-12-01 |  | Mystic #250 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2018-04-17 | [5 empty] | 23900000 | 23900000 | 23900000 | 23900000 | 23900000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000
Asset Condition | 1a | 53 | MA | National Grid, USA |  |  | 2024-06-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 2 | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [6 empty] | 12353000 | 12353000 | 11353000 | 11353000 | 11353000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 17732000 | 17732000 | 17732000 | 17732000 | 17732000 | 17732000
Asset Condition | 1a | 63 | MA | Eversource |  |  | 2023-12-01 |  | Lexington Station #320 Asset Condition Upgrade Project | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2020-07-01 | [6 empty] | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000
Asset Condition | 1a | 90 | MA | Eversource |  |  | 2024-12-01 |  | Canal Station #980 BPS and Asset Condition Upgrade Project | [8 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2020-06-30 | [8 empty] | 17923000 | 17923000 | 17923000 | 17923000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 41237000
Asset Condition | 1a | 145 | MA | National Grid, USA |  |  | 2024-05-01 |  | Carpenter Hill Control House Rebuild | [9 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-04-11 | [9 empty] | 6860000 | 6860000 | 6860000 | 6860000 | 6860000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000
Asset Condition | 1a | 146 | MA | National Grid, USA |  |  | 2024-05-01 |  | 327 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [9 empty] | 60400000 | 60400000 | 60400000 | 60400000 | 60400000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000
Asset Condition | 1a | 149 | MA | National Grid, USA |  |  | 2024-12-01 |  | 315 Line Asset Condition Refurbishments - MA Portion | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [9 empty] | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000
Asset Condition | 1a | 194 | MA | Eversource |  |  | 2023-12-01 |  | 110-510 & 110-511 lines 115 kV HPFF refurbishment | [11 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2020-04-29 | 2022-06-03 | [11 empty] | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 97995000 | 97995000 | 97995000 | 97995000 | 97995000 | 97995000 | 97995000
Asset Condition | 1a | 237 | MA | National Grid, USA |  |  | 2029-12-01 |  | A-1 & B-2 69 kV Line Asset Condition Project | [13 empty] | Concept | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | 2020-06-02 | No | [17 empty] | 347300000 | 347300000 | 347300000 | 325430000 | 325430000 | 325430000 | 325430000
Asset Condition | 1a | 250 | MA | Eversource |  |  | 2024-12-11 |  | Copper Conductor and Shield Wire Replacement - Line 1231/1242 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | 2022-10-19 | No | [15 empty] | 97000000 | 97000000 | 97000000 | 97000000 | 97000000 | 158500000 | 158504000 | 158504000 | 158504000
Asset Condition | 1a | 294 | MA | National Grid, USA |  |  | 2025-08-01 |  | Millbury #2 Substation Protection Scheme Upgrade and Asset Condition Refurbishments | [17 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-04-11 | [17 empty] | 28040000 | 28040000 | 28040000 | 28040000 | 28040000 | 28040000 | 28040000
Asset Condition | 1a | 297 | MA | Eversource |  |  | 2025-12-01 |  | 282-520 & 282-521 115 kV Lines HPFF Refurbishment | [17 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2021-08-23 | No | [17 empty] | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000
Asset Condition | 1a | 315 | MA | Eversource |  |  | 2023-12-01 |  | 115 kV Structure Replacements and Shield Wire - 191 Line | [18 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2023-02-07 | [18 empty] | 19200000 | 19200000 | 27840000 | 27840000 | 27840000 | 27840000
Asset Condition | 1a | 317 | MA | Eversource |  |  | 2025-12-11 |  | Edgar Station #150 Brown Glass and Obsolete Equipment Replacement | [18 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | NR | [18 empty] | 6500000 | 6500000 | 6500000 | 6500000 | 4000000 | 4000000
Asset Condition | 1a | 333 | MA | National Grid, USA |  |  | 2025-08-01 |  | Construct new Stafford Street Substation | [20 empty] | Planned | Under Construction | Under Construction | Under Construction | 2020-06-02 | 2023-05-31 | [20 empty] | 56800000 | 56800000 | 56800000 | 56870000
Asset Condition | 1a | 339 | MA | Eversource |  |  | 2024-03-01 |  | Northfield Mountain Substation 345 kV Breaker Replacements | [20 empty] | Proposed | Proposed | Proposed | Under Construction | NR | No | [20 empty] | 9200000 | 9200000 | 9200000 | 9005000
Asset Condition | 1a | 340 | MA | Eversource |  |  | 2023-12-01 |  | Holbrook Station 345/115 kV Autotransformer Replacement | [20 empty] | Proposed | Under Construction | Under Construction | Under Construction | 2022-09-22 | No | [20 empty] | 10290000 | 10155000 | 10155000 | 10155000
Asset Condition | 1a | 364 | MA | Eversource |  |  | 2024-06-01 |  | High Hill Station 644 Control House Replacement | [21 empty] | Planned | Planned | Under Construction | NR | No | [21 empty] | 19270000 | 19270000 | 19270000
Asset Condition | 1a | 365 | MA | Eversource |  |  | 2024-03-01 |  | Asset Condition Wood Structure Replacements - 389 345 kV Line | [21 empty] | Planned | Planned | Under Construction | NR | No | [21 empty] | 6648000 | 6648000 | 6648000
Asset Condition | 1a | 417 | MA | National Grid, USA |  |  | 2024-07-01 |  | Northboro Road Substation Breaker Replacements | [23 empty] | Under Construction | NR | No | [23 empty] | 5230000
Asset Condition | 1b | 421 | MA | Eversource |  |  | 2025-12-01 |  | NERC CIP-014 - Physical Security Upgrades - Round 1 | [23 empty] | Under Construction | No | No | [23 empty] | 121092000
Connecticut
Asset Condition | 1a | 19 | CT | United Illuminating Company |  |  | 2023-12-01 | UI Coastal Substation Flood Mitigation Study Project | Congress 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-07-19 |  |  |  | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 31770000 | 31770000 | 31770000 | 35190000 | 35190000 | 35190000 | 35190000
Asset Condition | 1a | 20 | CT | United Illuminating Company |  |  | 2024-04-01 | UI Coastal Substation Flood Mitigation Study Project | Grand Avenue - Mill River 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | No |  |  |  | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 41800000 | 41800000 | 41800000 | 41800000 | 41800000 | 41800000 | 41800000
Asset Condition | 1a | 21 | CT | United Illuminating Company |  |  | 2024-04-01 | UI Coastal Substation Flood Mitigation Study Project | Singer 345kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-05-17 |  |  |  | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 21960000 | 21960000 | 21960000 | 26450000 | 26450000 | 26450000 | 26450000
Asset Condition | 1a | 22 | CT | United Illuminating Company |  |  | 2024-09-01 | UI Coastal Substation Flood Mitigation Study Project | Pequonnock 115kV Substation rebuild with a new substation adjacent to the existing one |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2016-12-28 | 2022-04-11 |  |  |  | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 106100000 | 106106899 | 106106899 | 106106899 | 106106899 | 106106899
Asset Condition | 1a | 91 | CT | United Illuminating Company |  |  | 2025-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809A-2 Line (Pequonnock-Congress) | [8 empty] | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [8 empty] | 376300000 |  | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 151 | CT | United Illuminating Company |  |  | 2025-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809B-2 Line (Pequonnock - Congress) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 152 | CT | United Illuminating Company |  |  | 2028-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild portion of 1130 Line (Pequonnock - UI Str. B737) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614
Asset Condition | 1a | 153 | CT | United Illuminating Company |  |  | 2028-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 1430 Line (Ash Creek - ESE Str. B648) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220
Asset Condition | 1a | 154 | CT | United Illuminating Company |  |  | 2026-08-08 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 91001-1 Line (Pequonnock - Bridgeport Resco) & 91001-2 Line (Bridgeport Resco - Ash Creek) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324
Asset Condition | 1a | 155 | CT | United Illuminating Company |  |  | 2026-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005A-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 69080000 | 69080000 | 69080000
Asset Condition | 1a | 156 | CT | United Illuminating Company |  |  | 2026-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005B-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 69080000 | 69080000 | 69080000
Asset Condition | 1a | 157 | CT | United Illuminating Company |  |  | 2027-11-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804A Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 51810000 | 51810000 | 51810000
Asset Condition | 1a | 158 | CT | United Illuminating Company |  |  | 2027-11-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804B Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 51810000 | 51810000 | 51810000
Asset Condition | 1a | 159 | CT | United Illuminating Company |  |  | 2025-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 25905000 | 25905000 | 25905000
Asset Condition | 1a | 160 | CT | United Illuminating Company |  |  | 2025-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 25905000 | 25905000 | 25905000
Asset Condition | 1a | 161 | CT | United Illuminating Company |  |  | 2024-10-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 25905000 | 25905000 | 25905000
Asset Condition | 1a | 162 | CT | United Illuminating Company |  |  | 2024-10-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 25905000 | 25905000 | 25905000
Asset Condition | 1a | 178 | CT | Eversource |  |  | 2024-03-01 |  | 345 kV Structure Replacement Projects - Line 3754 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [11 empty] | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000
Asset Condition | 1a | 213 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1000 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | 2023-06-05 | [12 empty] | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 13690000 | 13690000
Asset Condition | 1a | 216 | CT | Eversource |  |  | 2024-06-01 |  | 115 kV Wood Pole Replacement - 1080 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | 2023-06-05 | [12 empty] | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 23574000 | 23574000 | 23574000
Asset Condition | 1a | 239 | CT | United Illuminating Company |  |  | 2025-01-01 |  | Derby Junction to Ansonia Corridor 115 kV Transmission Upgrades | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | NR | No | [13 empty] | 22374000 | 22374000 | 22374000 | 22374000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 70986666
Asset Condition | 1a | 260 | CT | Eversource |  |  | 2023-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1825 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2021-12-16 | No | [15 empty] | 7300000 | 7300000 | 7300000 | 7286000 | 7286000 | 7286000 | 7286000 | 7286000 | 7286000
Asset Condition | 1a | 266 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 387 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-23 | [15 empty] | 10200000 | 10200000 | 10200000 | 12781000 | 12781000 | 12781000 | 12781000 | 12781000 | 12781000
Asset Condition | 1a | 267 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3041 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-23 | [15 empty] | 14400000 | 14534000 | 14534000 | 14534000 | 14534000 | 14534000 | 14534000 | 14534000 | 14534000
Asset Condition | 1a | 269 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3754 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | NR | [15 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 4400000 | 4400000
Asset Condition | 1a | 352 | CT | Eversource |  |  | 2025-06-01 |  | Trumbull - Norwalk Corridor Partial 115 kV Line Rebuilds - 1637/1720 and 1714/1720/1222 Lines | [21 empty] | Proposed | Proposed | Under Construction | 2023-01-19 | No | [21 empty] | 159590000 | 159590000 | 159590000
Asset Condition | 1a | 357 | CT | Eversource |  |  | 2024-06-01 |  | 115 kV Line Asset Condition and OPGW Project - Line 1772 | [21 empty] | Under Construction | Under Construction | Under Construction | NR | No | [21 empty] | 20730000 | 20730000 | 20730000
Asset Condition | 1a | 359 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Structure Replacements and OPGW Installation - 362 Line | [21 empty] | Under Construction | Under Construction | Under Construction | NR | No | [21 empty] | 19163000 | 19163000 | 19163000
Asset Condition | 1a | 360 | CT | Eversource |  |  | 2024-06-01 |  | East Devon 345/115 kV Relay Upgrades | [21 empty] | Under Construction | Under Construction | Under Construction | NR | No | [21 empty] | 6720000 | 6720000 | 6720000
Asset Condition | 1a | 361 | CT | Eversource |  |  | 2023-12-01 |  | 115kV Lattice Tower and Shield Wire Replacements - 1261/1598 Line | [21 empty] | Proposed | Proposed | Under Construction | NR | No | [21 empty] | 5600000 | 5600000 | 7273000
Asset Condition | 1a | 371 | CT | Eversource |  |  | 2023-12-01 |  | South Naugatuck to Devon Rebuild - Segment 1 (Stevenson substation - Pootatuck substation) | [22 empty] | Under Construction | Under Construction | 2023-09-20 | No | [22 empty] | 87289000 | 87289000
Asset Condition | 1a | 376 | CT | Eversource |  |  | 2025-12-01 |  | CT Asset Condition Project - Card to Montville Corridor (Reconductor/OPGW lines 1000 and 1090, OPGW lines 1070, 1080, 1490) | [22 empty] | Under Construction | Under Construction | No | No | [22 empty] | 37198000 | 37198000
Asset Condition | 1a | 378 | CT | Eversource |  |  | 2024-03-01 |  | CT Asset Condition Project - Line 1620 | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 8821000 | 8821000
Rhode Island
Asset Condition | 1a | 150 | RI | Rhode Island Energy |  |  | 2025-06-01 |  | 315 Line Asset Condition Refurbishments - RI Portion | [9 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | 2021-01-29 | [9 empty] | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000
Asset Condition | 1a | 335 | RI | Rhode Island Energy |  |  | 2024-12-01 |  | G-185S/L-190 115 kV OPGW Installation from Davisville Tap to West Kingston (L-190 to Wickford Junction) | [20 empty] | Planned | Under Construction | Under Construction | Under Construction | NR | No | [20 empty] | 8493000 | 8493000 | 8493000 | 8493000
Table B
Maine
New Hampshire
Asset Condition | 1b | 97 | NH | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 382 | NH | Eversource |  |  | 2025-03-01 |  | NH Asset Condition Project - F139 Line | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 58000000 | 46628000
Asset Condition | 1b | 387 | NH | Eversource |  |  | 2026-12-01 |  | Northern New Hampshire 115kV Line Rebuilds - Q195 Line | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 100000000 | 100000000
Asset Condition | 1b | 388 | NH | Eversource |  |  | 2026-06-01 |  | Northern New Hampshire 115kV Line Rebuilds - U199 Line | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 51180000 | 51180000
Asset Condition | 1b | 389 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - 391 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 12370000 | 12370000
Asset Condition | 1b | 390 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - 373 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 10280000 | 10280000
Asset Condition | 1b | 391 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - R193 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 7700000 | 7700000
Asset Condition | 1b | 392 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - S153 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 5000000 | 5000000
Asset Condition | 1b | 393 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - A126 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 8370000 | 8370000
Asset Condition | 1b | 396 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - D121 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 5000000 | 5036000
Asset Condition | 1b | 398 | NH | Eversource |  |  | 2024-03-01 |  | NH Wood Structure Replacements and OPGW Installation - B143 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 17280000 | 17275000
Asset Condition | 1b | 403 | NH | Eversource |  |  | 2024-03-01 |  | Laminated Wood Structure Replacement Program Phase III - M108 | [23 empty] | Proposed | NR | No | [23 empty] | 13399000
Asset Condition | 1b | 404 | NH | Eversource |  |  | 2024-12-01 |  | Laminated Wood Structure Replacement Program Phase III - V182 | [23 empty] | Proposed | NR | No | [23 empty] | 32915000
Asset Condition | 1b | 406 | NH | Eversource |  |  | 2025-09-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - A164 | [23 empty] | Proposed | NR | No | [23 empty] | 66960000
Asset Condition | 1b | 407 | NH | Eversource |  |  | 2024-09-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - R169 | [23 empty] | Proposed | NR | No | [23 empty] | 8400000
Asset Condition | 1b | 408 | NH | Eversource |  |  | 2024-12-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - F162 | [23 empty] | Proposed | NR | No | [23 empty] | 21840000
Asset Condition | 1b | 409 | NH | Eversource |  |  | 2025-03-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - G146 | [23 empty] | Proposed | NR | No | [23 empty] | 58380000
Asset Condition | 1b | 410 | NH | Eversource |  |  | 2024-09-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - I158 | [23 empty] | Proposed | NR | No | [23 empty] | 28630000
Asset Condition | 1b | 411 | NH | Eversource |  |  | 2025-06-01 |  | Deerfield 345/115 kV Relay Upgrades | [23 empty] | Proposed | NR | No | [23 empty] | 5820000
Vermont
Massachusetts
Asset Condition | 1b | 94 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 95 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 96 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 236 | MA | National Grid, USA |  |  | 2028-11-01 |  | Deerfield #4 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No
Asset Condition | 1b | 293 | MA | Eversource |  |  | 2026-06-01 |  | Ludlow 19S 345 kV Full BPS Separation and Asset Condition Project | [16 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [16 empty] | 42900000 | 42900000 | 42900000 | 42900000 | 42900000 | 42900000 | 42900000 | 61520000
Asset Condition | 1b | 328 | MA | National Grid, USA |  |  | 2026-12-01 |  | Bridgewater #16 Substation Asset Condition Upgrades | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [19 empty] | 25950000 | 25950000 | 25950000 | 25950000 | 25950000
Asset Condition | 1b | 336 | MA | National Grid, USA |  |  | 2027-05-01 |  | Tewksbury #22 Substation Asset Condition Replacements | [20 empty] | Proposed | Proposed | Proposed | Proposed | No | No | [20 empty] | 35490000 | 35490000 | 35490000 | 35490000
Asset Condition | 1b | 337 | MA | National Grid, USA |  |  | 2030-12-01 |  | E-5/F-6 69kV Line Asset Condition Refurbishments | [20 empty] | Concept | Concept | Concept | Concept | 2022-07-11 | No
Asset Condition | 1b | 354 | MA | National Grid, USA |  |  | 2025-08-01 |  | Maplewood #16 Substation Asset Replacements | [21 empty] | Proposed | Proposed | Proposed | NR | 2023-09-12 | [21 empty] | 6170000 | 6170000 | 6170000
Asset Condition | 1b | 384 | MA | National Grid, USA |  |  | 2028-08-01 |  | Shutesbury #704 Substation Rebuild | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 8900000 | 8900000
Asset Condition | 1b | 385 | MA | National Grid, USA |  |  | 2027-10-01 |  | E-131 Asset Condition Refurbishment | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 138300000 | 138300000
Asset Condition | 1b | 400 | MA | National Grid, USA |  |  | 2030-03-31 |  | Adams #21 Substation Relocation | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 55100000 | 55100000
Asset Condition | 1b | 418 | MA | National Grid, USA |  |  | 2024-07-01 |  | 308 345 kV Line Asset Condition Refurbishment | [23 empty] | Proposed | NR | No | [23 empty] | 15770000
Asset Condition | 1b | 419 | MA | National Grid, USA |  |  | 2026-07-01 |  | S8 115 kV Line Asset Condition Project | [23 empty] | Proposed | No | No | [23 empty] | 88240000
Asset Condition | 1b | 420 | MA | National Grid, USA |  |  | 2029-03-01 |  | V5/U6 115 kV Line Asset Condition Project | [23 empty] | Proposed | No | No | [23 empty] | 131980000
Connecticut
Asset Condition | 1b | 258 | CT | Eversource |  |  | 2024-06-01 |  | Copper Conductor and Shield Wire Replacement - Line 1268/1485/1622/1887 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [15 empty] | 29600000 | 29600000 | 29600000 | 29600000 | 29600000 | 29600000 | 47200000 | 47200000 | 47200000
Asset Condition | 1b | 259 | CT | Eversource |  |  | 2024-09-01 |  | Copper Conductor and Shield Wire Replacement - Line 1163/1550 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 2023-02-23 | No | [15 empty] | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 34500000 | 34500000 | 34486000
Asset Condition | 1b | 338 | CT | Eversource |  |  | 2026-06-01 |  | Millstone Substation 345 kV Breaker Replacements | [20 empty] | Proposed | Proposed | Proposed | Proposed | NR | No | [20 empty] | 17600000 | 17600000 | 17600000 | 17600000
Asset Condition | 1b | 356 | CT | Eversource |  |  | 2024-06-01 |  | 115 kV Line Asset Condition and OPGW Project - Line 348 | [21 empty] | Proposed | Proposed | Proposed | No | No | [21 empty] | 8400000 | 8400000 | 8400000
Asset Condition | 1b | 358 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Structure Replacements and OPGW Installation - 3041 Line | [21 empty] | Proposed | Proposed | Proposed | NR | No | [21 empty] | 11600000 | 11600000 | 11600000
Asset Condition | 1b | 362 | CT | Eversource |  |  | 2024-06-01 |  | 115kV Lattice Tower, Shield Wire, and Conductor Replacements - 1355/1610 Line | [21 empty] | Proposed | Proposed | Proposed | No | No | [21 empty] | 50400000 | 50400000 | 50400000
Asset Condition | 1b | 363 | CT | Eversource |  |  | 2024-03-01 |  | Asset Condition Wood Structure Replacements - 1208 115 kV Line | [21 empty] | Proposed | Proposed | Proposed | NR | No | [21 empty] | 5842000 | 5842000 | 5842000
Asset Condition | 1b | 372 | CT | Eversource |  |  | 2025-12-01 |  | South Naugatuck to Devon Rebuild - Segment 2 (Pootatuck substation - West Devon Jct.) | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 46090000 | 46090000
Asset Condition | 1b | 373 | CT | Eversource |  |  | 2025-12-01 |  | South Naugatuck to Devon Rebuild - Segment 3 (West Devon Jct. - Devon substation) | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 41110000 | 41110000
Asset Condition | 1b | 374 | CT | Eversource |  |  | 2025-12-01 |  | South Naugatuck to Devon Rebuild - Segment 4 (Christian Street Jct. - Stevenson substation) | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 52960000 | 52960000
Asset Condition | 1b | 375 | CT | Eversource |  |  | 2025-12-01 |  | South Naugatuck to Devon Rebuild - Segment 5 (Towantic substation - South Naugatuck substation) | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 115100000 | 115100000
Asset Condition | 1b | 377 | CT | Eversource |  |  | 2024-06-01 |  | CT Asset Condition Project - Line 376 | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 9020000 | 9020000
Asset Condition | 1b | 379 | CT | Eversource |  |  | 2024-03-01 |  | CT Asset Condition Project - Lines 1132 and 1505 | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 13383000 | 13383000
Asset Condition | 1b | 412 | CT | Eversource |  |  | 2026-12-01 |  | 1704 Underground Cable Rebuild Project | [23 empty] | Proposed | No | No | [23 empty] | 169300000
Asset Condition | 1b | 413 | CT | Eversource |  |  | 2024-09-01 |  | Structure Replacements & OPGW Installations - 364 Line | [23 empty] | Proposed | NR | No | [23 empty] | 12610000
Asset Condition | 1b | 414 | CT | Eversource |  |  | 2024-09-01 |  | Structure Replacements & OPGW Installations - 348 Line | [23 empty] | Proposed | NR | No | [23 empty] | 9700000
Asset Condition | 1b | 415 | CT | Eversource |  |  | 2025-03-01 |  | Structure Replacements & OPGW Installations - 1726 Line | [23 empty] | Proposed | NR | No | [23 empty] | 8863000
Asset Condition | 1b | 416 | CT | Eversource |  |  | 2024-12-01 |  | Southington 115 kV Relay Upgrades | [23 empty] | Proposed | NR | No | [23 empty] | 13850000
Asset Condition | 1b | 423 | CT | Eversource |  |  | 2026-12-01 |  | 1722 Underground Cable Rebuild Project | [23 empty] | Proposed | No | No | [23 empty] | 132300000
Rhode Island
Asset Condition | 1b | 99 | RI | Rhode Island Energy |  |  | 2025-08-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
In-Service
Maine
Asset Condition | 1a | 23 | ME | MEPCO |  |  | 2019-06-01 |  | Section 388 & 3023 Structure Replacement |  |  |  | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-10 |  |  |  | 101600000 | 101600000 | 101600000 | 82400000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000
Asset Condition | 1a | 24 | ME | MEPCO |  |  | 2020-09-01 |  | Section 396 & 3001 Structure Replacement |  |  |  | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-10 |  |  |  | 16900000 | 16900000 | 16900000 | 16900000 | 16000000 | 16000000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000
Vermont
Asset Condition | 1a | 3 | VT | Vermont Electric Power Company |  |  | 2017-05-01 | Essex STATCOM Refurbishment | Replace Essex STATCOM power electronics and controls | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-08-13 | 27850000 | 27850000 | 27850000 | 27850000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000
Asset Condition | 1a | 11 | VT | Vermont Electric Power Company |  |  | 2018-12-01 | Structure Condition Improvement | Replacement of 115 kV, 230 kV and 345 kV structures as part of the VELCO asset maintenance activities addressing our aging and degrading transmission line infrastructure. 100 to 300 structures will be replaced every year based on outage availability |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-12-01 |  | 185000000 | 185000000 | 185000000 | 160200000 | 160200000 | 160200000 | 160200000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000
Asset Condition | 1a | 195 | VT | Vermont Electric Power Company |  |  | 2021-07-01 |  | Sand Bar Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers, switches | [11 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [11 empty] | 10600000 | 10600000 | 10600000 | 10600000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000
Asset Condition | 1a | 196 | VT | Vermont Electric Power Company |  |  | 2020-12-01 |  | Berlin Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers & switches. Install a second protection system. | [11 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 5872719 | 5550000 | 5550000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000
Asset Condition | 1a | 233 | VT | Vermont Electric Power Company |  |  | 2020-12-01 |  | Line K41 Asset Condition Structure Refurbishment | [13 empty] | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-01-29 | [13 empty] | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000
Asset Condition | 1a | 283 | VT | Vermont Electric Power Company |  |  | 2022-12-01 |  | Line K22 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2021-08-20 | [15 empty] | 9720000 | 9720000 | 9720000 | 9720000 | 9720000 | 9720000 | 8300000 | 8300000 | 8300000
Asset Condition | 1a | 285 | VT | Vermont Electric Power Company |  |  | 2022-12-01 |  | Line K34 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2021-08-20 | [15 empty] | 6710000 | 6710000 | 6710000 | 6710000 | 6710000 | 6710000 | 7750000 | 7750000 | 7750000
New Hampshire
Asset Condition | 1a | 4 | NH | New Hampshire Transmission |  |  | 2016-11-01 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 1 - Remove Breaker 22, remove Bus 4 and upgrade sections of Bus 2 | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-02-23 | 2018-09-11 | 5140351 | 5140351 | 5140351 | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($11.2) | Cost Part of Asset Condition #5 ($11.2)
Asset Condition | 1a | 5 | NH | New Hampshire Transmission |  |  | 2017-11-01 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 2 - Remove Breaker 11 and upgrade sections of Bus 1 | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-02-23 | 2018-09-11 | 4271787 | 4271787 | 4271787 | 11991000 | 11991000 | 11991000 | 11991000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1a | 35 | NH | Eversource |  |  | 2017-06-01 |  | Scobie Pond TB30 345/115 kV transformer replacement project |  |  |  |  | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2017-05-24 | 2018-08-24 |  |  |  |  | 10300000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000
Asset Condition | 1a | 36 | NH | Eversource |  |  | 2018-03-01 |  | Install two 40 MVAR reactors on the Scobie 115 kV bus, to accommodate the loss of the reactors connected on the 13.8 kV teriary winding of the TB30 transformer |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2017-05-24 | 2018-08-24 |  |  |  |  | 5200000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000
Asset Condition | 1a | 51 | NH | Eversource |  |  | 2018-07-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Deerfield TB-14 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-01-29 | 2020-10-08 | [5 empty] | 7700000 | 4779000 | 4779000 | 5300000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000
Asset Condition | 1a | 52 | NH | Eversource |  |  | 2018-11-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Littleton TB-41 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-01-29 | NR | [5 empty] | 6200000 | 3891000 | 3891000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000
Asset Condition | 1a | 55 | NH | Eversource |  |  | 2018-07-01 |  | 345 kV Structure Replacement Project - Line 307 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 12900000 | 12900000 | 12900000 | 12900000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000
Asset Condition | 1a | 56 | NH | Eversource |  |  | 2018-08-05 |  | 345 kV Structure Replacement Project - Line 326 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 12300000 | 12300000 | 12300000 | 12300000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000
Asset Condition | 1a | 57 | NH | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 367 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 15800000 | 15800000 | 15800000 | 15800000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000
Asset Condition | 1a | 58 | NH | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 379 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000
Asset Condition | 1a | 59 | NH | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 381 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13600000 | 13600000 | 13600000 | 13600000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000
Asset Condition | 1a | 60 | NH | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 391 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 19600000 | 19600000 | 19600000 | 19600000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000
Asset Condition | 1a | 85 | NH | New Hampshire Transmission |  |  | 2019-12-01 | Seabrook 345 kV GIS Switchyard Like-for Like Equipment Replacement | Phase 1 of mulit-phase project involving like for like equipment replacement. Phase 1 included replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345kV Seabrook-to-Timberswamp 369 line. Post-top insulators for the 369 line located in the open-air to GIS transition yard were also replaced. A bridge covering the GILs where they go below grade and then resurface upon entering the fenced-in Protected Area where the GIS Switchyard is located was replaced during this phase. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-04-21 | [6 empty] | 77017000 | 77017000 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778
Asset Condition | 1a | 86 | NH | New Hampshire Transmission |  |  | 2020-11-01 | Seabrook 345 kV GIS Switchyard Phase 2 Equipment Replacement Part of Asset Condition #85 | Phase 2 of mulit-phase project involving like for like equipment replacement. Phase 2 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345 kV Seabrook-Scobie Pond 363 line, and replacing two GIS 345 kV Circuit Breakers and related switches that are the 363 line termination equipment. Post-top insulators for the 363 line located in the open-air to GIS transition yard will also be replaced. Phase 2 also includes replacing Breaker Failure Relay Protection Systems for the 363 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 87 | NH | New Hampshire Transmission |  |  | 2022-06-01 | Seabrook 345 kV GIS Switchyard Phase 3 Equipment Replacement Part of Asset Condition #85 | Phase 3 of multi-phase project involving like for like equipment replacement. Phase 3 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345 kV Seabrook-Ward Hill 394 line, and replacing two GIS 345 kV Circuit Breakers and related switches that are the 394 line termination equipment. Post-top insulators located in the open-air to GIS transition yard will also be replaced. Phase 3 also includes replacing Breaker Failure Relay Protection Systems for the 394 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 100 | NH | Eversource |  |  | 2020-01-01 |  | 115 kV Structure Replacement Project - Line A126 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 8300000 | 8300000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000
Asset Condition | 1a | 101 | NH | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line H123 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 6000000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000
Asset Condition | 1a | 102 | NH | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line H141 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 7700000 | 7700000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000
Asset Condition | 1a | 103 | NH | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line K174 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 8700000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000
Asset Condition | 1a | 104 | NH | Eversource |  |  | 2021-02-01 |  | 115 kV Structure Replacement Project - Line L163 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 14000000 | 14000000 | 14000000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000
Asset Condition | 1a | 105 | NH | Eversource |  |  | 2020-09-01 |  | 115 kV Structure Replacement Project - Line A152 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 6100000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000
Asset Condition | 1a | 186 | NH | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 326 | [11 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [11 empty] | 5200000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000
Asset Condition | 1a | 187 | NH | Eversource |  |  | 2021-02-01 |  | 345 kV Structure Replacement Projects - Line 367 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 14100000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000
Asset Condition | 1a | 188 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 373 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 10300000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000
Asset Condition | 1a | 189 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 379 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 9700000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000
Asset Condition | 1a | 190 | NH | Eversource |  |  | 2020-01-01 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 8300000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000
Asset Condition | 1a | 191 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 385 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 14000000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000
Asset Condition | 1a | 192 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 391 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 16400000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000
Asset Condition | 1a | 198 | NH | Eversource |  |  | 2020-09-01 |  | 115 kV Wood Pole Replacement - B143 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 7410000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000
Asset Condition | 1a | 199 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole Replacement - C129 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2/2/2021 6/3/2022 | [12 empty] | 9100000 | 9045000 | 9045000 | 9045000 | 9045000 | 9045000 | 10048000 | 10048000 | 10048000 | 10048000 | 10048000 | 10048000
Asset Condition | 1a | 200 | NH | Eversource |  |  | 2021-06-01 |  | 115 kV Wood Pole Replacement - F139 | [12 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 8000000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000
Asset Condition | 1a | 201 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole Replacement - G128 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 6910000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000
Asset Condition | 1a | 202 | NH | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole Replacement - K105 | [12 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [12 empty] | 6080000 | 6080000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000
Asset Condition | 1a | 203 | NH | Eversource |  |  | 2022-04-01 |  | 115 kV Wood Pole and Shield Wire Replacement - K174 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 14740000 | 14740000 | 14740000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000
Asset Condition | 1a | 204 | NH | Eversource |  |  | 2020-03-01 |  | 115 kV Wood Pole Replacement - L175 | [12 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [12 empty] | 5250000 | 5250000 | 5250000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000
Asset Condition | 1a | 205 | NH | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - M127 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 33430000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000
Asset Condition | 1a | 206 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole and Shield Wire Replacement - Y138 | [12 empty] | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 8490000 | 8490000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000
Asset Condition | 1a | 273 | NH | Eversource |  |  | 2021-12-01 |  | Copper Conductor and Shield Wire Replacement Projects - C129 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | No | [15 empty] | 18500000 | 12145000 | 12145000 | 12145000 | 12145000 | 12145000 | 12145000 | 12145000 | 12145000
Asset Condition | 1a | 274 | NH | Eversource |  |  | 2022-01-01 |  | Copper Conductor and Shield Wire Replacement Projects - D108 Line | [15 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | 2021-09-22 | No | [15 empty] | 6700000 | 6700000 | 6750000 | 6750000 | 6750000 | 6750000 | 6750000 | 6750000 | 6750000
Asset Condition | 1a | 275 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - G128 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | No | [15 empty] | 7600000 | 5044000 | 5044000 | 5044000 | 5044000 | 5044000 | 5044000 | 5044000 | 5044000
Asset Condition | 1a | 276 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - L163 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | No | [15 empty] | 23300000 | 23310000 | 23310000 | 23310000 | 23310000 | 23310000 | 23310000 | 23310000 | 23310000
Asset Condition | 1a | 277 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - X104 | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | No | [15 empty] | 6994000 | 6994000 | 6994000 | 6994000 | 6994000 | 6994000 | 6994000 | 6994000 | 6994000
Asset Condition | 1a | 278 | NH | Eversource |  |  | 2022-11-01 |  | Amherst substation Protection & Controls Upgrades | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2021-08-21 | [15 empty] | 6100000 | 6100000 | 6100000 | 6100000 | 6081000 | 6081000 | 6081000 | 6081000 | 6081000
Asset Condition | 1a | 279 | NH | Eversource |  |  | 2022-09-01 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - A111 Line | [15 empty] | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | 2021-07-15 | 2023-05-31 | [15 empty] | 35940000 | 35940000 | 53501000 | 53501000 | 53501000 | 53501000 | 53501000 | 31227000 | 31227000
Asset Condition | 1a | 282 | NH | Eversource |  |  | 2022-04-01 |  | 345 kV Line Structure Replacements - Line 373 | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 9351000 | 9351000 | 9351000 | 9351000 | 9351000 | 9351000 | 9351000 | 9351000 | 9351000
Asset Condition | 1a | 286 | NH | Eversource |  |  | 2021-12-01 |  | Eddy Substation Control House Relocation and Rebuild | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2019-07-10 | 2021-08-23 | [16 empty] | 6051000 | 6051000 | 6051000 | 6051000 | 6051000 | 6051000 | 6051000 | 6051000
Asset Condition | 1a | 287 | NH | Eversource |  |  | 2021-11-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - G128 Line | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 12632000 | 12632000 | 12632000 | 12632000 | 12632000 | 12632000 | 12632000 | 12632000
Asset Condition | 1a | 288 | NH | Eversource |  |  | 2021-09-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - L175 Line | [16 empty] | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 19300000 | 19300000 | 19300000 | 19300000 | 19300000 | 19300000 | 19300000 | 19300000
Asset Condition | 1a | 289 | NH | Eversource |  |  | 2022-05-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - K105 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 14700000 | 14700000 | 16503000 | 16503000 | 16503000 | 16503000 | 16503000 | 16503000
Asset Condition | 1a | 290 | NH | Eversource |  |  | 2022-12-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - X116 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 26000000 | 26000000 | 24646000 | 24646000 | 24646000 | 24646000 | 24646000 | 24646000
Asset Condition | 1a | 291 | NH | Eversource |  |  | 2022-12-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - Z119 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 25400000 | 25400000 | 23443000 | 23443000 | 23443000 | 23443000 | 23443000 | 23443000
Asset Condition | 1a | 298 | NH | Eversource |  |  | 2022-06-01 |  | 115 kV Structure and Shield Wire Replacements - Line D121 | [17 empty] | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 13105000 | 13105000 | 13105000 | 13105000 | 13105000 | 13105000 | 13105000
Asset Condition | 1a | 321 | NH | Eversource |  |  | 2023-04-01 |  | Laminated Wood Structure Replacement Program Phase II - A152 115 kV Line | [18 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | 2023-06-01 | [18 empty] | 15264000 | 17476000 | 17476000 | 17476000 | 17476000 | 17476000
Asset Condition | 1a | 322 | NH | Eversource |  |  | 2022-09-01 |  | Laminated Wood Structure Replacement Program Phase II - V191 115 kV Line | [18 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | NR | 2023-06-01 | [18 empty] | 11024000 | 10114000 | 10114000 | 10114000 | 10114000 | 10114000
Asset Condition | 1a | 323 | NH | Eversource |  |  | 2022-12-01 |  | 115 kV Structure and Shield Wire Replacements - T198 Line | [18 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 19100000 | 19113000 | 19113000 | 19113000 | 19113000 | 19113000
Asset Condition | 1a | 324 | NH | Eversource |  |  | 2023-06-01 |  | P145 Line Rebuild - Asset Condition and OPGW | [18 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | 2022-08-19 | 2023-07-27 | [18 empty] | 52000000 | 52000000 | 52142000 | 52142000 | 52142000 | 52142000
Asset Condition | 1a | 325 | NH | Eversource |  |  | 2022-11-01 |  | Laminated Wood Structure Replacement Program Phase II - R187 115 kV Line | [18 empty] | Proposed | Proposed | Under Construction | In-service | In-service | In-service | NR | 2023-06-01 | [18 empty] | 7541000 | 7541000 | 7541000 | 7541000 | 7541000 | 7541000
Asset Condition | 1a | 326 | NH | Eversource |  |  | 2022-09-01 |  | Laminated Wood Structure Replacement Program Phase II - S188 115 kV Line | [18 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | NR | 2023-06-01 | [18 empty] | 7342000 | 7342000 | 7342000 | 7342000 | 7342000 | 7342000
Asset Condition | 1a | 327 | NH | Eversource |  |  | 2022-02-01 |  | Laminated Wood Structure Replacement Program Phase II - M164 115 kV Line | [18 empty] | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-01 | [18 empty] | 6024000 | 6024000 | 6024000 | 6024000 | 6024000 | 6024000
Asset Condition | 1a | 341 | NH | Eversource |  |  | 2023-06-01 |  | Deerfield Station 345 kV Breaker Replacements | [20 empty] | Under Construction | Under Construction | Under Construction | In-service | NR | No | [20 empty] | 5182000 | 5182000 | 5182000 | 5182000
Asset Condition | 1a | 342 | NH | Eversource |  |  | 2022-11-01 |  | Line 379 Asset Condition Wood Structure Replacements | [20 empty] | Under Construction | In-service | In-service | In-service | NR | No | [20 empty] | 8020000 | 8020000 | 8020000 | 8020000
Asset Condition | 1a | 344 | NH | Eversource |  |  | 2023-02-01 |  | Line 373 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | In-service | In-service | NR | No | [20 empty] | 7066000 | 7066000 | 7066000 | 7066000
Asset Condition | 1a | 345 | NH | Eversource |  |  | 2023-03-01 |  | Line 326 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | In-service | In-service | NR | No | [20 empty] | 6194000 | 6194000 | 6194000 | 6194000
Asset Condition | 1a | 346 | NH | Eversource |  |  | 2023-02-01 |  | Line 385 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | In-service | In-service | NR | No | [20 empty] | 5035000 | 5035000 | 5035000 | 5035000
Asset Condition | 1a | 347 | NH | Eversource |  |  | 2023-02-01 |  | Line 391 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | In-service | In-service | NR | No | [20 empty] | 8953000 | 8953000 | 8953000 | 8953000
Asset Condition | 1a | 348 | NH | Eversource |  |  | 2023-06-01 |  | Line C196 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | Under Construction | In-service | NR | No | [20 empty] | 14800000 | 14800000 | 11690000 | 11690000
Asset Condition | 1a | 366 | NH | Eversource |  |  | 2023-02-01 |  | Eagle Substation 345/115 kV Autotransformer Replacement | [21 empty] | Under Construction | In-service | In-service | 2022-09-22 | 2023-04-28 | [21 empty] | 6375000 | 6375000 | 6375000
Asset Condition | 1a | 369 | NH | Eversource |  |  | 2023-08-01 |  | Asset Condition Wood Structure Replacements - C196 115 kV Line | [21 empty] | Proposed | Proposed | In-service | NR | No | [21 empty] | 6191000 | 6191000 | 6191000
Asset Condition | 1a | 381 | NH | Eversource |  |  | 2023-05-01 |  | NH Asset Condition Project - M183 Line | [22 empty] | Under Construction | In-service | NR | No | [22 empty] | 6000000 | 6000000
Connecticut
Asset Condition | 1a | 6 | CT | Eversource |  |  | 2014-09-01 |  | 1570 line clearance remediation. Devon S/S to Beacon Falls S/S. 31 conductor span locations were found to have NESC clearance discrepancies. | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 | 6500000 | 6500000 | 6500000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000
Asset Condition | 1a | 16 | CT | Eversource |  |  | 2016-06-01 |  | 3419 line (portion in Connecticut) asset condition and storm hardening. Asset conditon - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1
Asset Condition | 1a | 17 | CT | United Illuminating Company |  |  | 2020-06-01 |  | East Shore 345 kV circuit switcher replacement project. Replace 345 kV circuit switchers with dead tank breakers |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In Service | In Service | In Service | In Service | In Service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-07-19 | 2019-10-30 |  |  | 10931000 | 10931000 | 10931000 | 10931000 | 9234000 | 9234000 | 9234000 | 9234000 | 9234000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000
Asset Condition | 1a | 18 | CT | United Illuminating Company |  |  | 2020-06-01 | UI Coastal Substation Flood Mitigation Study Project | East Shore - Raising Impacted 115 kV Equipment |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In Service | In Service | In Service | In Service | In Service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-10-30 |  |  |  | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000
Asset Condition | 1a | 29 | CT | Eversource |  |  | 2017-09-01 |  | 1620/1975 line structure replacement |  |  |  | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/1/2017 2/19/2021 |  |  |  | 15500000 | 12500000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000
Asset Condition | 1a | 30 | CT | Eversource |  |  | 2016-12-01 |  | 3424 line Asset Condition and Storm Hardening |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  |  | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000
Asset Condition | 1a | 33 | CT | Eversource |  |  | 2017-06-01 |  | 1410 and 100 Line Structure Replacements |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-12-01 |  |  |  |  | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000
Asset Condition | 1a | 34 | CT | Eversource |  |  | 2018-12-01 |  | Devon Control House Modifications |  |  |  |  | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-04-17 |  |  |  |  | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000
Asset Condition | 1a | 39 | CT | Eversource |  |  | 2017-11-01 |  | 3419 line (portion in Connecticut) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-02 |  |  |  |  | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38
Asset Condition | 1a | 46 | CT | Eversource |  |  | 2017-12-01 |  | Southern CT Loop Line Structure Replacements - 1261/1598 115 kV | [5 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-04-17 | [5 empty] | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000
Asset Condition | 1a | 47 | CT | Eversource |  |  | 2019-05-01 |  | Southern CT Loop Line Structure Replacements - 1342 115 kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-10 | [5 empty] | 30300000 | 30300000 | 30300000 | 30300000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000
Asset Condition | 1a | 48 | CT | Eversource |  |  | 2018-07-01 |  | Southern CT Loop Line Structure Replacements - 1508 115 kV | [5 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-08-24 | [5 empty] | 16600000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000
Asset Condition | 1a | 49 | CT | Eversource |  |  | 2020-01-01 |  | Southern CT Loop Line Structure Replacements - 1655 115 kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-06-30 | [5 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 17100000 | 17100000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000
Asset Condition | 1a | 50 | CT | Eversource |  |  | 2019-11-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Card 11F-5X autotransformer. Foundation and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-05-16 | NR | [5 empty] | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000
Asset Condition | 1a | 67 | CT | Eversource |  |  | 2022-05-01 |  | Manchester Control House Expansion | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2020-10-08 | [6 empty] | 21400000 | 21400000 | 21400000 | 21400000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000
Asset Condition | 1a | 68 | CT | Eversource |  |  | 2019-04-01 |  | Card-Montville-Tunnel Corridor Asset Condition and OPGW Installation Project | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 | [6 empty] | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000
Asset Condition | 1a | 69 | CT | Eversource |  |  | 2018-12-01 |  | Oil Circuit Breaker Replacement Project at the Frost Bridge Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-08-24 | [6 empty] | 7250000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000
Asset Condition | 1a | 70 | CT | Eversource |  |  | 2020-04-01 |  | Oil Circuit Breaker Replacement Project at the Plumtree Substation | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-12-22 | [6 empty] | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000
Asset Condition | 1a | 71 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 310 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 16500000 | 16500000 | 16500000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000
Asset Condition | 1a | 72 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 321 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/16/2019 2/19/202 | [6 empty] | 6000000 | 6000000 | 6000000 | 5847000 | 5847000 | 5847000 | 5847000 | 5847000 | 5847000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000
Asset Condition | 1a | 73 | CT | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 330 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13500000 | 13500000 | 13500000 | 13500000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000
Asset Condition | 1a | 74 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 348 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 16000000 | 16000000 | 16000000 | 16000000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000
Asset Condition | 1a | 75 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 364 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 14300000 | 14300000 | 14300000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000
Asset Condition | 1a | 76 | CT | Eversource |  |  | 2020-05-01 |  | 345 kV Structure Replacement Project - Line 371 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/16/2019 2/19/2020 | [6 empty] | 10600000 | 10600000 | 10600000 | 11546000 | 11546000 | 11546000 | 11546000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000
Asset Condition | 1a | 77 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 383 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 15500000 | 15500000 | 15500000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000
Asset Condition | 1a | 78 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 387 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13100000 | 13100000 | 13100000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000
Asset Condition | 1a | 79 | CT | Eversource |  |  | 2018-05-01 |  | 345 kV Structure Replacement Project - Line 398 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 7800000 | 7800000 | 7800000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000
Asset Condition | 1a | 80 | CT | Eversource |  |  | 2018-07-01 |  | 345 kV Structure Replacement Project - Line 3041 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 9700000 | 9700000 | 9700000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000
Asset Condition | 1a | 81 | CT | Eversource |  |  | 2018-09-01 |  | 345 kV Structure Replacement Project - Line 3642 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 9900000 | 9900000 | 9900000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000
Asset Condition | 1a | 82 | CT | Eversource |  |  | 2020-05-01 |  | Laminated Structure Replacement Project - Line 1505/1607 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000
Asset Condition | 1a | 83 | CT | Eversource |  |  | 2020-05-01 |  | Laminated Structure Replacement Project - Line 1675/1080 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000
Asset Condition | 1a | 84 | CT | Eversource |  |  | 2018-12-01 |  | Laminated Structure Replacement Project - Line 1921 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000
Asset Condition | 1a | 89 | CT | Eversource |  |  | 2020-06-01 |  | Montville 16X Transformer Replacement | [7 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-05-16 | NR | [7 empty] | 6300000 | 6300000 | 6300000 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676
Asset Condition | 1a | 115 | CT | Eversource |  |  | 2019-09-01 |  | 1608 115 kV Line Cable Replacement | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2019-12-19 | 2020-04-28 | [9 empty] | 11300000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000
Asset Condition | 1a | 116 | CT | Eversource |  |  | 2019-01-01 |  | 1880 115 kV Line Cable Replacement | [9 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-04-28 | [9 empty] | 7200000 | 7200000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000
Asset Condition | 1a | 117 | CT | Eversource |  |  | 2019-05-01 |  | 115 kV Structure Replacement Project - Line 1050 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7300000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000
Asset Condition | 1a | 119 | CT | Eversource |  |  | 2019-06-01 |  | 115 kV Structure Replacement Project - Line 1256 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12200000 | 12200000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000
Asset Condition | 1a | 120 | CT | Eversource |  |  | 2020-10-01 |  | 115 kV Structure Replacement Project - Line 1261/1598 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2/19/2021 5/31/2022 | [9 empty] | 18300000 | 18300000 | 18300000 | 20352000 | 20352000 | 20352000 | 20352000 | 20352000 | 20352000 | 23854000 | 23854000 | 23854000 | 23854000 | 23854000 | 23854000
Asset Condition | 1a | 122 | CT | Eversource |  |  | 2021-03-01 |  | 115 kV Structure Replacement Project - Line 1310 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8300000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000
Asset Condition | 1a | 124 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Structure Replacement Project - Line 1448 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 6900000 | 6926000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000
Asset Condition | 1a | 125 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1565 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 11500000 | 11500000 | 11500000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000
Asset Condition | 1a | 126 | CT | Eversource |  |  | 2019-04-01 |  | 115 kV Structure Replacement Project - Line 1620 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 10000000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000
Asset Condition | 1a | 127 | CT | Eversource |  |  | 2021-02-01 |  | 115 kV Structure Replacement Project - Line 1635 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5700000 | 5764000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000
Asset Condition | 1a | 129 | CT | Eversource |  |  | 2020-08-01 |  | 115 kV Structure Replacement Project - Line 1726 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 16300000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000
Asset Condition | 1a | 130 | CT | Eversource |  |  | 2021-12-01 |  | 115 kV Structure Replacement Project - Line 1465 | [9 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7000000 | 7000000 | 7000000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000
Asset Condition | 1a | 131 | CT | Eversource |  |  | 2018-11-01 |  | 115 kV Structure Replacement Project - Line 1751 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 12500000 | 12500000 | 12500000 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | 4467000 | 4467000 | 4467000 | 4467000 | 4467000 | 4467000 | 4467000
Asset Condition | 1a | 133 | CT | Eversource |  |  | 2018-09-01 |  | 115 kV Structure Replacement Project - Line 1759 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7300000 | 7300000 | 7300000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000
Asset Condition | 1a | 134 | CT | Eversource |  |  | 2020-11-01 |  | 115 kV Structure Replacement Project - Line 1765 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12300000 | 12300000 | 12300000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000
Asset Condition | 1a | 135 | CT | Eversource |  |  | 2018-06-01 |  | 115 kV Structure Replacement Project - Line 1766 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5800000 | 5800000 | 5800000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000
Asset Condition | 1a | 136 | CT | Eversource |  |  | 2018-04-01 |  | 115 kV Structure Replacement Project - Line 1767 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5400000 | 5400000 | 5400000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000
Asset Condition | 1a | 137 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1769 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8200000 | 8200000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000
Asset Condition | 1a | 138 | CT | Eversource |  |  | 2018-10-01 |  | 115 kV Structure Replacement Project - Line 1770 (the 1770 line has been replaced by the Plumtree to Stony Hill 1268 line and the Stony Hill to Bates Rock 1485 line) | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 16300000 | 16300000 | 16300000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000
Asset Condition | 1a | 139 | CT | Eversource |  |  | 2021-08-07 |  | 115 kV Structure Replacement Project - Line 1772 | [9 empty] | In-service | In-service | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 10000000 | 10000000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000
Asset Condition | 1a | 140 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1783 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8200000 | 8200000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000
Asset Condition | 1a | 141 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1785 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 9000000 | 9000000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000
Asset Condition | 1a | 142 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1768-CT | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5200000 | 5200000 | 5200000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000
Asset Condition | 1a | 143 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1910 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5800000 | 5800000 | 5800000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000
Asset Condition | 1a | 144 | CT | Eversource |  |  | 2021-10-01 |  | Millstone Substation 15G High Creep Insulator Replacement | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2020-10-08 | [9 empty] | 11500000 | 11500000 | 11500000 | 11500000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000
Asset Condition | 1a | 163 | CT | Eversource |  |  | 2020-12-01 |  | 667 69 kV line rebuild and asset condition project | [10 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 7/25/2019 8/28/2020 | 2020-04-28 | [10 empty] | 24080000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000
Asset Condition | 1a | 164 | CT | Eversource |  |  | 2022-03-01 |  | 345 kV Structure Replacement Projects - Line 310 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 19900000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000
Asset Condition | 1a | 165 | CT | Eversource |  |  | 2019-12-01 |  | 345 kV Structure Replacement Projects - Line 321 | [11 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 6500000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000
Asset Condition | 1a | 166 | CT | Eversource |  |  | 2021-11-01 |  | 345 kV Structure Replacement Projects - Line 330 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000
Asset Condition | 1a | 167 | CT | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Projects - Line 348 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 19400000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000
Asset Condition | 1a | 168 | CT | Eversource |  |  | 2020-06-01 |  | 345 kV Structure Replacement Projects - Line 352 | [11 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 12500000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000
Asset Condition | 1a | 169 | CT | Eversource |  |  | 2019-08-07 |  | 345 kV Structure Replacement Projects - Line 362 | [11 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000
Asset Condition | 1a | 170 | CT | Eversource |  |  | 2022-07-01 |  | 345 kV Structure Replacement Projects - Line 364 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 17300000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000
Asset Condition | 1a | 171 | CT | Eversource |  |  | 2019-12-01 |  | 345 kV Structure Replacement Projects - Line 368 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 7300000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000
Asset Condition | 1a | 172 | CT | Eversource |  |  | 2022-03-01 |  | 345 kV Structure Replacement Projects - Line 383 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-01 | [11 empty] | 22200000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000
Asset Condition | 1a | 173 | CT | Eversource |  |  | 2021-11-01 |  | 345 kV Structure Replacement Projects - Line 387 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-01 | [11 empty] | 18200000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000
Asset Condition | 1a | 174 | CT | Eversource |  |  | 2019-07-01 |  | 345 kV Structure Replacement Projects - Line 3041 | [11 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000
Asset Condition | 1a | 175 | CT | Eversource |  |  | 2019-10-01 |  | 345 kV Structure Replacement Projects - Line 3252 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000
Asset Condition | 1a | 176 | CT | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-01 | [11 empty] | 11900000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000
Asset Condition | 1a | 177 | CT | Eversource |  |  | 2019-07-01 |  | 345 kV Structure Replacement Projects - Line 3424 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 7900000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000
Asset Condition | 1a | 193 | CT | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Projects - Line 1470 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [11 empty] | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000
Asset Condition | 1a | 197 | CT | United Illuminating Company |  |  | 2019-10-01 |  | 1130 Line Optical Ground Wire (OPGW) Replacement | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-10-30 | [11 empty] | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000
Asset Condition | 1a | 214 | CT | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole Replacement - 1042 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 6080000 | 6080000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000
Asset Condition | 1a | 215 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1043 | [12 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000
Asset Condition | 1a | 217 | CT | Eversource |  |  | 2021-08-01 |  | 115 kV Wood Pole Replacement - 1208 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 8960000 | 8960000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000
Asset Condition | 1a | 218 | CT | Eversource |  |  | 2021-10-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1232 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | NR | [12 empty] | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 2422000 | 2422000 | 2422000 | 2422000 | 2422000 | 2422000
Asset Condition | 1a | 219 | CT | Eversource |  |  | 2022-08-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1256 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 10640000 | 10640000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000
Asset Condition | 1a | 220 | CT | Eversource |  |  | 2023-08-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1280 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | 2023-06-05 | [12 empty] | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 13956000 | 19726000 | 19726000 | 19726000
Asset Condition | 1a | 221 | CT | Eversource |  |  | 2022-09-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1410 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 13000000 | 13000000 | 13000000 | 10091000 | 10091000 | 10091000 | 10091000 | 8353000 | 8353000 | 8353000 | 8353000 | 8353000
Asset Condition | 1a | 222 | CT | Eversource |  |  | 2020-06-01 |  | 115 kV Wood Pole Replacement - Line 1505 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000
Asset Condition | 1a | 223 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Wood Pole Replacement - 1607 | [12 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000
Asset Condition | 1a | 224 | CT | Eversource |  |  | 2022-05-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1618 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | 2020-08-28 | 2023-06-05 | [12 empty] | 9770000 | 9770000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000
Asset Condition | 1a | 225 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1732 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 7900000 | 7900000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000
Asset Condition | 1a | 227 | CT | Eversource |  |  | 2021-11-01 |  | 115 kV Wood Pole Replacement - 1756 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 24469000 | 24469000 | 24469000 | 24469000 | 24469000 | 24469000 | 24469000
Asset Condition | 1a | 228 | CT | Eversource |  |  | 2021-04-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1765 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | NR | [12 empty] | 14700000 | 14700000 | 8801000 | 8801000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000
Asset Condition | 1a | 229 | CT | Eversource |  |  | 2021-02-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1766 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 16600000 | 16600000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000
Asset Condition | 1a | 230 | CT | Eversource |  |  | 2022-06-01 |  | 115 kV Wood Pole Replacement - 1910 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 10300000 | 10300000 | 10300000 | 10300000 | 10300000 | 10300000 | 8226000 | 8226000 | 8226000 | 8226000 | 8226000 | 8226000
Asset Condition | 1a | 231 | CT | Eversource |  |  | 2020-04-01 |  | 115 kV Line Rebuild and Asset Condition Project - Line 1355 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [12 empty] | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000
Asset Condition | 1a | 241 | CT | Eversource |  |  | 2021-05-01 |  | Glenbrook STATCOM Replacement | [14 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2021-04-14 | 8/21/2021 12/23/2022 | [14 empty] | 21600000 | 21624000 | 18699000 | 18699000 | 18699000 | 18699000 | 21298000 | 21298000 | 21298000 | 21298000
Asset Condition | 1a | 242 | CT | Eversource |  |  | 2021-08-07 |  | Horton Cove Asset Condition and OPGW Project | [14 empty] | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2020-11-06 | 2022-06-01 | [14 empty] | 13400000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000
Asset Condition | 1a | 243 | CT | Eversource |  |  | 2021-06-01 |  | 115 kV Lattice Tower Asset Condition and OPGW Project - Line 1768 | [14 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2020-11-06 | 2021-08-21 | [14 empty] | 22600000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000
Asset Condition | 1a | 244 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Copper Conductor and Wood Pole Replacement - Line 1191 | [14 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2020-10-05 | 2021-08-21 | [14 empty] | 38050000 | 38050000 | 38054000 | 38054000 | 38054000 | 38054000 | 38054000 | 38054000 | 38054000 | 38054000
Asset Condition | 1a | 245 | CT | Eversource |  |  | 2022-04-01 |  | Southington Substation Relay Replacement Project | [15 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2021-08-21 | [15 empty] | 9400000 | 9362000 | 9362000 | 9362000 | 9362000 | 9362000 | 9362000 | 9362000 | 9362000
Asset Condition | 1a | 246 | CT | Eversource |  |  | 2018-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 329 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-28 | [15 empty] | 5925000 | 5925000 | 5925000 | 5925000 | 5925000 | 5925000 | 5925000 | 5925000 | 5925000
Asset Condition | 1a | 247 | CT | Eversource |  |  | 2018-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 352 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-28 | [15 empty] | 5998000 | 5998000 | 5998000 | 5998000 | 5998000 | 5998000 | 5998000 | 5998000 | 5998000
Asset Condition | 1a | 257 | CT | Eversource |  |  | 2021-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1588 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2021-06-17 | No | [15 empty] | 9600000 | 9600000 | 9611000 | 9611000 | 9611000 | 9611000 | 9611000 | 9611000 | 9611000
Asset Condition | 1a | 261 | CT | Eversource |  |  | 2022-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement 2020-2023 - Line 1465 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [15 empty] | 8770000 | 8770000 | 8770000 | 8770000 | 8770000 | 8770000 | 8770000 | 8770000 | 8770000
Asset Condition | 1a | 262 | CT | Eversource |  |  | 2022-10-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 310 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 59200000 | 59200000 | 61333000 | 61333000 | 61333000 | 61333000 | 61333000 | 61333000 | 61333000
Asset Condition | 1a | 263 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure Replacement - Line 330 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 12/23/2022 4/25/2023 | [15 empty] | 6600000 | 6600000 | 8039000 | 8039000 | 8039000 | 8039000 | 10248000 | 10248000 | 10248000
Asset Condition | 1a | 264 | CT | Eversource |  |  | 2022-01-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 368 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 8800000 | 8800000 | 9860000 | 9860000 | 9860000 | 9860000 | 9860000 | 9860000 | 9860000
Asset Condition | 1a | 265 | CT | Eversource |  |  | 2023-02-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 383 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | NR | 2022-12-23 | [15 empty] | 16300000 | 16300000 | 16778000 | 16778000 | 16778000 | 16778000 | 16778000 | 16778000 | 16778000
Asset Condition | 1a | 268 | CT | Eversource |  |  | 2023-06-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3424 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | 2022-12-23 | [15 empty] | 14900000 | 14900000 | 14900000 | 14900000 | 14900000 | 14900000 | 14900000 | 14900000 | 14900000
Asset Condition | 1a | 292 | CT | Eversource |  |  | 2021-12-01 |  | Branford 11J A3 Bus Replacement Project | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-08-22 | [16 empty] | 10322000 | 10322000 | 10322000 | 10322000 | 10322000 | 10322000 | 10322000 | 10322000
Asset Condition | 1a | 302 | CT | Eversource |  |  | 2022-05-01 |  | 690 Line Rebuild and Asset Condition Project | [17 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-service | In-service | 2021-07-15 | 2023-04-28 | [17 empty] | 11000000 | 11000000 | 11045000 | 11045000 | 11045000 | 11045000 | 11045000
Asset Condition | 1a | 303 | CT | Eversource |  |  | 2022-06-01 |  | 115 kV Wood Pole Replacement - Line 1751 | [17 empty] | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 28800000 | 28794000 | 28794000 | 28794000 | 28794000 | 28794000 | 28794000
Asset Condition | 1a | 309 | CT | Eversource |  |  | 2023-03-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Glenbrook 115 kV | [18 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | No | [18 empty] | 10034000 | 10034000 | 10034000 | 10034000 | 10034000 | 10034000
Asset Condition | 1a | 310 | CT | Eversource |  |  | 2023-03-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Plumtree 115 kV and 345 kV | [18 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | No | [18 empty] | 19300000 | 19300000 | 19300000 | 19300000 | 19300000 | 19300000
Asset Condition | 1a | 311 | CT | Eversource |  |  | 2023-03-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Norwalk 115 kV and 345 kV | [18 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | No | [18 empty] | 16358000 | 16358000 | 16358000 | 16358000 | 16358000 | 16358000
Asset Condition | 1a | 312 | CT | Eversource |  |  | 2023-03-01 |  | Laminated Wood Structure Replacement Program Phase II - 3403 345 kV Line | [18 empty] | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | NR | 2023-06-01 | [18 empty] | 8422000 | 8422000 | 8422000 | 12091000 | 12091000 | 12091000
Asset Condition | 1a | 313 | CT | Eversource |  |  | 2022-04-01 |  | 345 kV Structure and Shield Wire Replacements - 329 Line | [18 empty] | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | NR | 2/7/2023 6/1/2023 | [18 empty] | 6242000 | 6242000 | 6242000 | 6927000 | 6927000 | 6927000
Asset Condition | 1a | 314 | CT | Eversource |  |  | 2022-06-01 |  | 345 kV Structure and Shield Wire Replacements - 352 Line | [18 empty] | Proposed | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5800000 | 5782000 | 5782000 | 5782000 | 5782000 | 5782000
Asset Condition | 1a | 355 | CT | Eversource |  |  | 2023-04-01 |  | 115 kV Structure Replacements and OPGW Installation - 1783 Line | [21 empty] | Under Construction | Under Construction | In-service | NR | 2023-07-27 | [21 empty] | 6285000 | 6285000 | 6285000
Asset Condition | 1a | 422 | CT | Eversource |  |  | 2020-12-01 |  | NERC CIP-014 - Physical Security Upgrades - Round 1 | [23 empty] | In-service | No | No | [23 empty] | 53527000
Massachusetts
Asset Condition | 1a | 1 | MA | Eversource |  |  | 2016-06-01 |  | 3419 line (portion in Massachusetts) asset condition and storm hardening. Asset condition - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 | 14500000 | 14500000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000
Asset Condition | 1a | 2 | MA | National Grid, USA |  |  | 2016-10-01 | Crystal Lake Substation Upgrades | Crystal Lake Substation Upgrades | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-05-05 | 2018-10-10 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000
Asset Condition | 1a | 7 | MA | Eversource |  |  | 2015-12-01 |  | 115 kV line 136 Falmouth Tap - West Barnstable Complete structure replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000
Asset Condition | 1a | 8 | MA | Eversource |  |  | 2015-05-01 |  | 381 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000
Asset Condition | 1a | 9 | MA | Eversource |  |  | 2015-12-01 |  | 354 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000
Asset Condition | 1a | 10 | MA | Eversource |  |  | 2014-07-01 |  | 312 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000
Asset Condition | 1a | 12 | MA | Eversource |  |  | 2017-07-01 |  | Doreen-Oswald Jct. 1211 115 kV Line Structure Replacement |  | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  | 14800000 | 14800000 | 14800000 | 11500000 | 11500000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000
Asset Condition | 1a | 13 | MA | Eversource |  |  | 2017-01-01 |  | Ludlow-Thorndike-Palmer (WMA portion) of the X176 115 KV Line Rebuild |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 |  | 14900000 | 8928000 | 8928000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000
Asset Condition | 1a | 14 | MA | Eversource |  |  | 2015-12-01 |  | 1231/1242 Line Clearance remediation Project |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 |  |  | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000
Asset Condition | 1a | 15 | MA | Eversource |  |  | 2019-05-01 |  | Install a new Medway control house which is to be built to BPS standards in a location within the existing station footprint. |  |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-01-26 | 2017-07-17 |  |  | 11800000 | 11800000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000
Asset Condition | 1a | 25 | MA | Taunton Municipal Light Plant |  |  | 2022-12-01 |  | Cleary 115 kV ring bus asset replacement - replace existing ring bus with new 115 kV switching station on an adjacent site and reconnect lines and transformers |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | No |  |  |  | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 6000000 | 6000000 | 6000000
Asset Condition | 1a | 28 | MA | Eversource |  |  | 2023-07-01 |  | 115 kV GIS breaker replacement at Kingston Street #514 Substation |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | 7/1/2020 4/28/2023 |  |  |  | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 46838000 | 46838000 | 46838000 | 46838000
Asset Condition | 1a | 31 | MA | Eversource |  |  | 2016-05-01 |  | 345 kV GIS breaker replacements at Kingston Street #514 |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-05-11 |  |  |  | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000
Asset Condition | 1a | 32 | MA | Eversource |  |  | 2020-12-01 |  | West Medway Substation #446 Asset Condition Upgrade |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2017-12-01 |  |  |  |  | 18900000 | 18900000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000
Asset Condition | 1a | 37 | MA | Eversource |  |  | 2018-11-01 |  | New Mt. Tom protection system control house |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 |  |  |  |  | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000
Asset Condition | 1a | 38 | MA | Eversource |  |  | 2017-12-01 |  | 3419 line (portion in Massachusetts) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  |  |  | 13700000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000
Asset Condition | 1a | 40 | MA | National Grid, USA |  | 1 | 2018-05-01 |  | Salem Harbor Substation - 115 kV oil circuit breaker replacements |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR |  |  |  |  | 6000000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000
Asset Condition | 1a | 41 | MA | Eversource |  |  | 2013-06-01 |  | Scotia Street Substation Project | [5 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-07-17 | [5 empty] | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000
Asset Condition | 1a | 42 | MA | Eversource |  |  | 2020-12-01 |  | Brighton #329 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2018-04-17 | [5 empty] | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000
Asset Condition | 1a | 45 | MA | Eversource |  |  | 2018-07-01 |  | 345 kV 354 Line Structure Replacements | [5 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 | [5 empty] | 10148000 | 10148000 | 7017000 | 7017000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000
Asset Condition | 1a | 61 | MA | Eversource |  |  | 2017-09-01 |  | 1231/1242 Structure Replacement Project | [6 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-02-15 | [6 empty] | 7966000 | 7966000 | 7966000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000
Asset Condition | 1a | 62 | MA | Eversource |  |  | 2018-12-01 |  | Oil Circuit Breaker Replacement Project at the Agawam Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [6 empty] | 5400000 | 5400000 | 5400000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Asset Condition | 1a | 64 | MA | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Project - Line 393 | [6 empty] | Proposed | Proposed | Proposed | In-service | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-16 | [6 empty] | 10000000 | 10000000 | 10000000 | 10000000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000
Asset Condition | 1a | 65 | MA | Eversource |  |  | 2020-06-01 |  | Laminated Structure Replacement Project - Line 1512 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000
Asset Condition | 1a | 66 | MA | Eversource |  |  | 2019-05-01 |  | Laminated Structure Replacement Project - Line 1211/1161 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12598500 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000
Asset Condition | 1a | 88 | MA | National Grid, USA |  |  | 2019-12-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [6 empty] | 1384000 | 1384000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2908881 | 2908881 | 2908881 | 2908881 | 2908881 | 2908881 | 2908881
Asset Condition | 1a | 92 | MA | National Grid, USA |  |  | 2022-08-01 |  | Robinson Avenue Station #102 Asset Condition Upgrades | [8 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | NR | 1/29/2021 10/31/2022 | [8 empty] | 8300000 | 8300000 | 8300000 | 8300000 | 10340000 | 10340000 | 10340000 | 10430000 | 10430000 | 14892000 | 14892000 | 18020000 | 18020000 | 18020000 | 18020000 | 18020000
Asset Condition | 1a | 107 | MA | Eversource |  |  | 2021-06-01 |  | 349X/Y 345 kV Cable Replacement | [9 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2019-10-07 | 2020-06-30 | [9 empty] | 72400000 | 72400000 | 72400000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000
Asset Condition | 1a | 108 | MA | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 65-508 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 19500000 | 19500000 | 19500000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000
Asset Condition | 1a | 109 | MA | Eversource |  |  | 2019-03-01 |  | 115 kV Structure Replacement Project - Line 1327 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 7800000 | 7800000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000
Asset Condition | 1a | 110 | MA | Eversource |  |  | 2019-03-01 |  | 115 kV Structure Replacement Project - Line 1428 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12100000 | 12100000 | 12100000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000
Asset Condition | 1a | 111 | MA | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1447 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 6600000 | 6600000 | 6600000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000
Asset Condition | 1a | 112 | MA | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line 1962 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 20300000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000
Asset Condition | 1a | 113 | MA | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1768-MA | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-18 | [9 empty] | 3000000 | 3000000 | 3000000 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142
Asset Condition | 1a | 114 | MA | Eversource |  |  | 2019-11-01 |  | 115 kV Structure Replacement Project - Line F132 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 11000000 | 11000000 | 11000000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000
Asset Condition | 1a | 147 | MA | National Grid, USA |  |  | 2022-02-01 |  | 303 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-31 | [9 empty] | 24700000 | 24700000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000
Asset Condition | 1a | 148 | MA | National Grid, USA |  |  | 2020-05-01 |  | 3520 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-31 | [9 empty] | 6900000 | 6900000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000
Asset Condition | 1a | 179 | MA | Eversource |  |  | 2019-10-01 |  | 345 kV Structure Replacement Projects - Line 336 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 6600000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000
Asset Condition | 1a | 180 | MA | Eversource |  |  | 2019-08-01 |  | 345 kV Structure Replacement Projects - Line 3361 | [11 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [11 empty] | 6300000 | 6300000 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951
Asset Condition | 1a | 181 | MA | Eversource |  |  | 2022-08-01 |  | 345 kV Structure Replacement Projects - Line 312 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000
Asset Condition | 1a | 182 | MA | Eversource |  |  | 2019-11-01 |  | 345 kV Structure Replacement Projects - Line 354 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 29600000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000
Asset Condition | 1a | 183 | MA | Eversource |  |  | 2019-09-01 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 12500000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000
Asset Condition | 1a | 184 | MA | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Project - Line 393 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 11000000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000
Asset Condition | 1a | 185 | MA | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Proposed | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 26000000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000
Asset Condition | 1a | 207 | MA | Eversource |  |  | 2021-10-01 |  | 115 kV Wood Pole Replacement - 1161 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2/2/2021 12/23/2022 | [12 empty] | 17100000 | 17100000 | 17100000 | 22578000 | 22578000 | 22578000 | 22578000 | 22578000 | 24992000 | 24992000 | 24992000 | 24992000
Asset Condition | 1a | 208 | MA | Eversource |  |  | 2022-09-01 |  | 115 kV Wood Pole Replacement - 1421 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 15750000 | 15750000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000
Asset Condition | 1a | 209 | MA | Eversource |  |  | 2020-10-01 |  | 115 kV Wood Pole Replacement - 1512 | [12 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000
Asset Condition | 1a | 210 | MA | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1394 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 7070000 | 7070000 | 7070000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000
Asset Condition | 1a | 211 | MA | Eversource |  |  | 2020-07-01 |  | 115 kV Wood Pole and Shield Wire Replacement - Line 1858 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000
Asset Condition | 1a | 212 | MA | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1976 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 7470000 | 7470000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000
Asset Condition | 1a | 238 | MA | Eversource |  |  | 2020-06-01 |  | 115 kV Granville Junction to Atwater 1853 line (formerly 1512) OPGW Project | [13 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | NR | [13 empty] | 5000000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000
Asset Condition | 1a | 240 | MA | National Grid, USA |  |  | 2022-10-01 | Boston 2028 Project | Rebuild the Golden Hills #90 Substation | [14 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-04-08 | [14 empty] | 9345000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000
Asset Condition | 1a | 248 | MA | Eversource |  |  | 2017-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 338 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-28 | [15 empty] | 5804000 | 5804000 | 5804000 | 5804000 | 5804000 | 5804000 | 5804000 | 5804000 | 5804000
Asset Condition | 1a | 249 | MA | Eversource |  |  | 2019-06-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 455-507 115 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-28 | [15 empty] | 10296000 | 10296000 | 10296000 | 10296000 | 10296000 | 10296000 | 10296000 | 10296000 | 10296000
Asset Condition | 1a | 251 | MA | Eversource |  |  | 2022-11-01 |  | 345 kV Line Structure Replacement - Line 312 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 12/23/2022 4/25/2023 | [15 empty] | 19300000 | 19300000 | 21160000 | 21160000 | 21160000 | 21160000 | 26739000 | 26739000 | 26739000
Asset Condition | 1a | 252 | MA | Eversource |  |  | 2021-06-01 |  | 345 kV Line Structure Replacement - Line 319 | [15 empty] | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 7800000 | 7800000 | 7838000 | 7838000 | 7838000 | 7838000 | 7838000 | 7838000 | 7838000
Asset Condition | 1a | 253 | MA | Eversource |  |  | 2021-10-01 |  | 345 kV Line Structure Replacement - Line 338 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000
Asset Condition | 1a | 254 | MA | Eversource |  |  | 2021-04-01 |  | 115 kV Wood Pole Asset Condition Project - Line 455-507 | [15 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-10-27 | [15 empty] | 5191000 | 5191000 | 5191000 | 5191000 | 5191000 | 5191000 | 5191000 | 5191000 | 5191000
Asset Condition | 1a | 270 | MA | National Grid, USA |  |  | 2022-06-01 |  | S-145/T-146 115 kV Line Reconductoring - North Reading Substation to Wallace Substation | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | 2020-12-11 | 2022-06-02 | [15 empty] | 16540000 | 16540000 | 16540000 | 16540000 | 16540000 | 21885000 | 21885000 | 21885000 | 21885000
Asset Condition | 1a | 271 | MA | National Grid, USA |  |  | 2023-04-01 |  | V-148S Asset Condition Refurbishment and Switch Replacement - MA Portion | [15 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | In-service | In-service | 2022-03-17 | 2023-01-30 | [15 empty] | 10411000 | 10411000 | 10411000 | 10411000 | 10411000 | 9780000 | 9780000 | 9780000 | 9780000
Asset Condition | 1a | 295 | MA | National Grid, USA |  |  | 2022-02-01 |  | C-129N/D-130 115 kV Line Fiber Installation | [17 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-04-11 | [17 empty] | 11220000 | 11220000 | 11220000 | 11220000 | 11220000 | 11220000 | 11220000
Asset Condition | 1a | 296 | MA | National Grid, USA |  |  | 2022-03-01 |  | X-176 115 kV Line Asset Condition Refurbishments | [17 empty] | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | 2022-04-11 | [17 empty] | 18520000 | 18520000 | 18520000 | 18520000 | 18520000 | 18520000 | 18520000
Asset Condition | 1a | 299 | MA | Eversource |  |  | 2021-12-01 |  | 115 kV Structure Replacements - Line 456-522 | [17 empty] | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 5672000 | 5672000 | 5672000 | 5672000 | 5672000 | 5672000 | 5672000
Asset Condition | 1a | 300 | MA | Eversource |  |  | 2021-11-01 |  | 115 kV Structure Replacements - Line 240-510 | [17 empty] | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 11636000 | 11636000 | 11636000 | 11636000 | 11636000 | 11636000 | 11636000
Asset Condition | 1a | 301 | MA | Eversource |  |  | 2021-11-01 |  | 230 kV Structure Replacements - Line 342-603 | [17 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 5451000 | 5451000 | 5451000 | 5451000 | 5451000 | 5451000 | 5451000
Asset Condition | 1a | 304 | MA | Eversource |  |  | 2021-04-01 |  | 478-508 & 478-509 115 kV Lines Asset Condition & OPGW | [17 empty] | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-05-31 | [17 empty] | 5866000 | 5866000 | 5866000 | 5866000 | 5866000 | 5866000 | 5866000
Asset Condition | 1a | 306 | MA | National Grid, USA |  |  | 2023-05-01 |  | V-174 115 kV Line Asset Condition Refurbishments and OPGW installation | [18 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | NR | 2022-10-31 | [18 empty] | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000
Asset Condition | 1a | 307 | MA | National Grid, USA |  |  | 2022-05-01 |  | M-139/N-140 115 kV Lines Pilot Protection Schemes | [18 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | NR | 2022-10-31 | [18 empty] | 9400000 | 9400000 | 9400000 | 10560000 | 10560000 | 10560000
Asset Condition | 1a | 316 | MA | Eversource |  |  | 2022-12-01 |  | 115 kV Structure Replacements and Shield Wire - 117 Line | [18 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5900000 | 5880000 | 5880000 | 5880000 | 5880000 | 5880000
Asset Condition | 1a | 318 | MA | Eversource |  |  | 2022-06-01 |  | 115 kV Structure Replacements - 211-508 Line | [18 empty] | Proposed | Proposed | In-service | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
Asset Condition | 1a | 319 | MA | Eversource |  |  | 2022-07-01 |  | 115 kV Structure Replacements - 391-508 Line | [18 empty] | Proposed | Proposed | In-service | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Asset Condition | 1a | 320 | MA | Eversource |  |  | 2022-08-01 |  | 115 kV Structure Replacements - 533-508 Line | [18 empty] | Proposed | Proposed | In-service | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Asset Condition | 1a | 329 | MA | Eversource |  |  | 2023-04-01 |  | 115 kV Line Structure and OPGW Replacements - Line 1428 | [19 empty] | Proposed | Proposed | Under Construction | In-service | In-service | 2022-07-20 | 2023-07-26 | [19 empty] | 7994000 | 7994000 | 7994000 | 7994000 | 7994000
Asset Condition | 1a | 334 | MA | National Grid, USA |  |  | 2023-05-01 |  | K-137/L-138W 115 kV Lines Pilot Protection Scheme | [20 empty] | Planned | Under Construction | In-service | In-service | NR | 2023-02-07 | [20 empty] | 19940000 | 19940000 | 20540000 | 20540000
Asset Condition | 1a | 353 | MA | National Grid, USA |  |  | 2022-11-01 |  | 326 345 kV Line Structure Replacements | [21 empty] | Under Construction | In-service | In-service | NR | No | [21 empty] | 8900000 | 8900000 | 8900000
Rhode Island
Asset Condition | 1a | 54 | RI | National Grid, USA |  |  | 2019-12-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | NR | [6 empty] | 427000 | 427000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1174157 | 1174157 | 1174157 | 1174157 | 1174157 | 1174157 | 1174157
Asset Condition | 1a | 272 | RI | Rhode Island Energy |  |  | 2022-12-01 |  | V-148S Asset Condition Refurbishment and Switch Replacement - RI Portion | [15 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-Service | In-service | In-service | 2022-03-17 | 2023-02-07 | [15 empty] | 14322000 | 14322000 | 14322000 | 14322000 | 14322000 | 14590000 | 14580000 | 14580000 | 14580000
CANCELLED PROJECTS
Asset Condition | 1a | 93 | VT | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No
Asset Condition | 1b | 98 | RI | Rhode Island Energy |  | 2 | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | NR | No
Asset Condition | 1b | 106 | NH | Eversource |  |  | 2023-12-11 |  | 115 kV Structure Replacement Project - Line X178 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1b | 118 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1191 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000
Asset Condition | 1b | 121 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1280 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000
Asset Condition | 1b | 123 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1410 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
Asset Condition | 1a | 128 | CT | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line 1675 | [9 empty] | Proposed | Under Construction | Cancelleed | Cancelleed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000
Asset Condition | 1b | 132 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1756 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7000000 | 7000000 | 7000000 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227
Asset Condition | 1b | 226 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1751 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [12 empty] | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000
Asset Condition | 1b | 234 | MA | National Grid, USA |  |  | 2026-10-01 |  | Chestnut Hill #702 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | No | No
Asset Condition | 1b | 255 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1560/1808 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | No | No | [15 empty] | 19700000 | 19700000 | 19700000 | 19700000 | 19700000 | 19700000 | 19700000 | 19700000 | 19700000
Asset Condition | 1b | 256 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1580/1142/1808 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | No | No | [15 empty] | 68100000 | 68100000 | 68100000 | 68100000 | 68100000 | 68100000 | 68100000 | 68100000 | 68100000
Notes:
1 The original cost for Asset Condition project #40 was above the $5 million threshold. The current project is close to the threshold so this project will remain on the list.
² Project #98 was cancelled as it was covered by RSP #1815 (L-190) and ACL #335 (G185S).
Asset Condition List - Status Definitions:
The Section #'s designate the "need" category of the project. Original categories are not changed when a project is placed In-service or Cancelled
Sections - These projects are Asset Condition Upgrades
1a: Planned or Under construction
1b: Concept or Proposed
Concept - Project is under consideration to address an asset condition issue that has been presented to PAC or TOPAC. Costs are not provided
Proposed - Asset owner has determined that the solution is appropriate to address the asset condition issue and the solution has been presented to the P A C. Costs must be provided
Planned - PPA has been approved, if needed. Costs must be provided
Under Construction - Implementation of project is underway Costs must be provided
In-service - Project is in-service. Costs must be provided
Description of PAC interaction and inclusion on the Asset Condition list:
1. If the asset condition issue is on PTF and the PTF cost is greater than $5M, a presentation will be made to the PAC and the project will be added to the Asset Condition list.
2. If the asset condition issue is on the PTF and non-PTF, a presentation will be made to the TOPAC and if the cost of the PTF portion is greater than $5M, a presentation will be made to the PAC and the project will be added to the Asset Condition list.
3. If the asset condition issue is only on the non-PTF, but the corrective action results in changes to the PTF, a presentation will be made to the TOPAC and the project will be added to the Asset Condition list. There is no requirement to discuss the project with the PAC.

## ACL_sortable
Primary Driver | Section # | Asset Condition ID | State | Primary Equipment Owner | Other Equipment Owner(s) | Footnote Number | Projected In-Service Month/Year | Asset Condition Grouping | Description | Mar-16 Status | Jun-16 Status | Oct-16 Status | Mar-17 Status | Jun-17 Status | Oct-17 Status | Mar-18 Status | Jun-18 Status | Oct-18 Status | Mar-19 Status | Jun-19 Status | Oct-19 Status | Mar-20 Status | Jun-20 Status | Oct-20 Status | Mar-21 Status | Jun-21 Status | Oct-21 Status | Mar-22 Status | Jun-22 Status | Oct-22 Status | Mar-23 Status | Jun-23 Status | Oct-23 Status | PPA (I.3.9) Approval | TCA Approval | Mar-16 Estimated PTF Costs | Jun-16 Estimated PTF Costs | Oct-16 Estimated PTF Costs | Mar-17 Estimated PTF Costs | Jun-17 Estimated PTF Costs | Oct-17 Estimated PTF Costs | Mar-18 Estimated PTF Costs | Jun-18 Estimated PTF Costs | Oct-18 Estimated PTF Costs | Mar-19 Estimated PTF Costs | Jun-19 Estimated PTF Costs | Oct-19 Estimated PTF Costs | Mar-20 Estimated PTF Costs | Jun-20 Estimated PTF Costs | Oct-20 Estimated PTF Costs | Mar-21 Estimated PTF Costs | Jun-21 Estimated PTF Costs | Oct-21 Estimated PTF Costs | Mar-22 Estimated PTF Costs | Jun-22 Estimated PTF Costs | Oct-22 Estimated PTF Costs | Mar-23 Estimated PTF Costs | Jun-23 Estimated PTF Costs | Oct-23 Estimated PTF Costs
Asset Condition | 1a | 1 | MA | Eversource |  |  | 2016-06-01 |  | 3419 line (portion in Massachusetts) asset condition and storm hardening. Asset condition - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 | 14500000 | 14500000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000 | 11014000
Asset Condition | 1a | 2 | MA | National Grid, USA |  |  | 2016-10-01 | Crystal Lake Substation Upgrades | Crystal Lake Substation Upgrades | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-05-05 | 2018-10-10 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 6950000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000 | 7630000
Asset Condition | 1a | 3 | VT | Vermont Electric Power Company |  |  | 2017-05-01 | Essex STATCOM Refurbishment | Replace Essex STATCOM power electronics and controls | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-08-13 | 27850000 | 27850000 | 27850000 | 27850000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000 | 27300000
Asset Condition | 1a | 4 | NH | New Hampshire Transmission |  |  | 2016-11-01 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 1 - Remove Breaker 22, remove Bus 4 and upgrade sections of Bus 2 | Proposed | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-02-23 | 2018-09-11 | 5140351 | 5140351 | 5140351 | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($12.0) | Cost Part of Asset Condition #5 ($11.2) | Cost Part of Asset Condition #5 ($11.2)
Asset Condition | 1a | 5 | NH | New Hampshire Transmission |  |  | 2017-11-01 | Seabrook 345 kV GIS Breaker Removal and Bus Upgrade | Phase 2 - Remove Breaker 11 and upgrade sections of Bus 1 | Proposed | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-02-23 | 2018-09-11 | 4271787 | 4271787 | 4271787 | 11991000 | 11991000 | 11991000 | 11991000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1a | 6 | CT | Eversource |  |  | 2014-09-01 |  | 1570 line clearance remediation. Devon S/S to Beacon Falls S/S. 31 conductor span locations were found to have NESC clearance discrepancies. | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 | 6500000 | 6500000 | 6500000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000 | 6437000
Asset Condition | 1a | 7 | MA | Eversource |  |  | 2015-12-01 |  | 115 kV line 136 Falmouth Tap - West Barnstable Complete structure replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000 | 20270000
Asset Condition | 1a | 8 | MA | Eversource |  |  | 2015-05-01 |  | 381 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000 | 14150000
Asset Condition | 1a | 9 | MA | Eversource |  |  | 2015-12-01 |  | 354 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000 | 13517000
Asset Condition | 1a | 10 | MA | Eversource |  |  | 2014-07-01 |  | 312 Line Structure Replacements | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2015-11-25 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000 | 8125000
Asset Condition | 1a | 11 | VT | Vermont Electric Power Company |  |  | 2018-12-01 | Structure Condition Improvement | Replacement of 115 kV, 230 kV and 345 kV structures as part of the VELCO asset maintenance activities addressing our aging and degrading transmission line infrastructure. 100 to 300 structures will be replaced every year based on outage availability |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-12-01 |  | 185000000 | 185000000 | 185000000 | 160200000 | 160200000 | 160200000 | 160200000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000 | 158000000
Asset Condition | 1a | 12 | MA | Eversource |  |  | 2017-07-01 |  | Doreen-Oswald Jct. 1211 115 kV Line Structure Replacement |  | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  | 14800000 | 14800000 | 14800000 | 11500000 | 11500000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000
Asset Condition | 1a | 13 | MA | Eversource |  |  | 2017-01-01 |  | Ludlow-Thorndike-Palmer (WMA portion) of the X176 115 KV Line Rebuild |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 |  | 14900000 | 8928000 | 8928000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000
Asset Condition | 1a | 14 | MA | Eversource |  |  | 2015-12-01 |  | 1231/1242 Line Clearance remediation Project |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2016-12-16 |  |  | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000 | 13804000
Asset Condition | 1a | 15 | MA | Eversource |  |  | 2019-05-01 |  | Install a new Medway control house which is to be built to BPS standards in a location within the existing station footprint. |  |  | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-01-26 | 2017-07-17 |  |  | 11800000 | 11800000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000 | 12287000
Asset Condition | 1a | 16 | CT | Eversource |  |  | 2016-06-01 |  | 3419 line (portion in Connecticut) asset condition and storm hardening. Asset conditon - replace 24 wood poles H-frame with direct embed steel wood pole equivalent or wood located in MA & CT. |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1 | Cost part of Asset Condition #1
Asset Condition | 1a | 17 | CT | United Illuminating Company |  |  | 2020-06-01 |  | East Shore 345 kV circuit switcher replacement project. Replace 345 kV circuit switchers with dead tank breakers |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In Service | In Service | In Service | In Service | In Service | In-service | In-service | In-service | In-service | In-service | In-service | 2016-07-19 | 2019-10-30 |  |  | 10931000 | 10931000 | 10931000 | 10931000 | 9234000 | 9234000 | 9234000 | 9234000 | 9234000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000 | 11240000
Asset Condition | 1a | 18 | CT | United Illuminating Company |  |  | 2020-06-01 | UI Coastal Substation Flood Mitigation Study Project | East Shore - Raising Impacted 115 kV Equipment |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In Service | In Service | In Service | In Service | In Service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-10-30 |  |  |  | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000 | 330000
Asset Condition | 1a | 19 | CT | United Illuminating Company |  |  | 2023-12-01 | UI Coastal Substation Flood Mitigation Study Project | Congress 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-07-19 |  |  |  | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 14800000 | 31770000 | 31770000 | 31770000 | 35190000 | 35190000 | 35190000 | 35190000
Asset Condition | 1a | 20 | CT | United Illuminating Company |  |  | 2024-04-01 | UI Coastal Substation Flood Mitigation Study Project | Grand Avenue - Mill River 115 kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | No |  |  |  | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 16600000 | 41800000 | 41800000 | 41800000 | 41800000 | 41800000 | 41800000 | 41800000
Asset Condition | 1a | 21 | CT | United Illuminating Company |  |  | 2024-04-01 | UI Coastal Substation Flood Mitigation Study Project | Singer 345kV Substation Flood Wall |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-05-17 |  |  |  | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 11600000 | 21960000 | 21960000 | 21960000 | 26450000 | 26450000 | 26450000 | 26450000
Asset Condition | 1a | 22 | CT | United Illuminating Company |  |  | 2024-09-01 | UI Coastal Substation Flood Mitigation Study Project | Pequonnock 115kV Substation rebuild with a new substation adjacent to the existing one |  |  |  | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2016-12-28 | 2022-04-11 |  |  |  | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 128200000 | 106100000 | 106106899 | 106106899 | 106106899 | 106106899 | 106106899
Asset Condition | 1a | 23 | ME | MEPCO |  |  | 2019-06-01 |  | Section 388 & 3023 Structure Replacement |  |  |  | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-10 |  |  |  | 101600000 | 101600000 | 101600000 | 82400000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000 | 72900000
Asset Condition | 1a | 24 | ME | MEPCO |  |  | 2020-09-01 |  | Section 396 & 3001 Structure Replacement |  |  |  | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-10 |  |  |  | 16900000 | 16900000 | 16900000 | 16900000 | 16000000 | 16000000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000 | 19900000
Asset Condition | 1a | 25 | MA | Taunton Municipal Light Plant |  |  | 2022-12-01 |  | Cleary 115 kV ring bus asset replacement - replace existing ring bus with new 115 kV switching station on an adjacent site and reconnect lines and transformers |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | NR | No |  |  |  | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 6000000 | 6000000 | 6000000
Asset Condition | 1a | 26 | MA | Eversource |  |  | 2023-12-01 |  | Rebuild Bourne Substation as a breaker and one half scheme |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2018-04-30 | 2021-08-21 |  |  |  | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 37000000 | 76000000 | 76000000 | 76000000 | 76000000 | 69893000 | 69893000 | 69893000 | 69893000 | 69893000 | 69893000 | 69893000 | 69893000
Asset Condition | 1a | 27 | MA | Eversource |  |  | 2023-12-11 |  | Kingston Substation #735 Asset Condition Replacement |  |  |  | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2018-04-30 | 2022-06-01 |  |  |  | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 6500000 | 10428000 | 10428000 | 10428000 | 10428000 | 10428000 | 10428000 | 10428000
Asset Condition | 1a | 28 | MA | Eversource |  |  | 2023-07-01 |  | 115 kV GIS breaker replacement at Kingston Street #514 Substation |  |  |  | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | 7/1/2020 4/28/2023 |  |  |  | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 34500000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 39082000 | 46838000 | 46838000 | 46838000 | 46838000
Asset Condition | 1a | 29 | CT | Eversource |  |  | 2017-09-01 |  | 1620/1975 line structure replacement |  |  |  | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/1/2017 2/19/2021 |  |  |  | 15500000 | 12500000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 11093000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000 | 13050000
Asset Condition | 1a | 30 | CT | Eversource |  |  | 2016-12-01 |  | 3424 line Asset Condition and Storm Hardening |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  |  | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000 | 5919000
Asset Condition | 1a | 31 | MA | Eversource |  |  | 2016-05-01 |  | 345 kV GIS breaker replacements at Kingston Street #514 |  |  |  | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-05-11 |  |  |  | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000 | 22208000
Asset Condition | 1a | 32 | MA | Eversource |  |  | 2020-12-01 |  | West Medway Substation #446 Asset Condition Upgrade |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2017-12-01 |  |  |  |  | 18900000 | 18900000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000 | 18870000
Asset Condition | 1a | 33 | CT | Eversource |  |  | 2017-06-01 |  | 1410 and 100 Line Structure Replacements |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-12-01 |  |  |  |  | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000 | 6467000
Asset Condition | 1a | 34 | CT | Eversource |  |  | 2018-12-01 |  | Devon Control House Modifications |  |  |  |  | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-04-17 |  |  |  |  | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000 | 9350000
Asset Condition | 1a | 35 | NH | Eversource |  |  | 2017-06-01 |  | Scobie Pond TB30 345/115 kV transformer replacement project |  |  |  |  | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2017-05-24 | 2018-08-24 |  |  |  |  | 10300000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000 | 7835000
Asset Condition | 1a | 36 | NH | Eversource |  |  | 2018-03-01 |  | Install two 40 MVAR reactors on the Scobie 115 kV bus, to accommodate the loss of the reactors connected on the 13.8 kV teriary winding of the TB30 transformer |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2017-05-24 | 2018-08-24 |  |  |  |  | 5200000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000 | 4710000
Asset Condition | 1a | 37 | MA | Eversource |  |  | 2018-11-01 |  | New Mt. Tom protection system control house |  |  |  |  | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 |  |  |  |  | 7700000 | 7700000 | 7700000 | 7700000 | 7700000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000 | 6657000
Asset Condition | 1a | 38 | MA | Eversource |  |  | 2017-12-01 |  | 3419 line (portion in Massachusetts) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-03 |  |  |  |  | 13700000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000 | 13421000
Asset Condition | 1a | 39 | CT | Eversource |  |  | 2017-11-01 |  | 3419 line (portion in Connecticut) asset condition and OPGW project |  |  |  |  | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-01-02 |  |  |  |  | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38 | Cost part of Asset Condition #38
Asset Condition | 1a | 40 | MA | National Grid, USA |  | 1 | 2018-05-01 |  | Salem Harbor Substation - 115 kV oil circuit breaker replacements |  |  |  |  | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR |  |  |  |  | 6000000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000 | 4600000
Asset Condition | 1a | 41 | MA | Eversource |  |  | 2013-06-01 |  | Scotia Street Substation Project | [5 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2017-07-17 | [5 empty] | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000 | 21060000
Asset Condition | 1a | 42 | MA | Eversource |  |  | 2020-12-01 |  | Brighton #329 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2018-04-17 | [5 empty] | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000 | 21000000
Asset Condition | 1a | 43 | MA | Eversource |  |  | 2023-11-01 |  | K Street #385 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2018-04-17 | [5 empty] | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000 | 18402000
Asset Condition | 1a | 44 | MA | Eversource |  |  | 2028-12-01 |  | Mystic #250 115 kV Control House | [5 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2018-04-17 | [5 empty] | 23900000 | 23900000 | 23900000 | 23900000 | 23900000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000 | 41113000
Asset Condition | 1a | 45 | MA | Eversource |  |  | 2018-07-01 |  | 345 kV 354 Line Structure Replacements | [5 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 | [5 empty] | 10148000 | 10148000 | 7017000 | 7017000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000 | 10148000
Asset Condition | 1a | 46 | CT | Eversource |  |  | 2017-12-01 |  | Southern CT Loop Line Structure Replacements - 1261/1598 115 kV | [5 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-04-17 | [5 empty] | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000 | 7551000
Asset Condition | 1a | 47 | CT | Eversource |  |  | 2019-05-01 |  | Southern CT Loop Line Structure Replacements - 1342 115 kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-10 | [5 empty] | 30300000 | 30300000 | 30300000 | 30300000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000 | 27560000
Asset Condition | 1a | 48 | CT | Eversource |  |  | 2018-07-01 |  | Southern CT Loop Line Structure Replacements - 1508 115 kV | [5 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-08-24 | [5 empty] | 16600000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000 | 15884000
Asset Condition | 1a | 49 | CT | Eversource |  |  | 2020-01-01 |  | Southern CT Loop Line Structure Replacements - 1655 115 kV | [5 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-06-30 | [5 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 17100000 | 17100000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000 | 18545000
Asset Condition | 1a | 50 | CT | Eversource |  |  | 2019-11-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Card 11F-5X autotransformer. Foundation and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-05-16 | NR | [5 empty] | 8600000 | 8600000 | 8600000 | 8600000 | 8600000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000 | 3700000
Asset Condition | 1a | 51 | NH | Eversource |  |  | 2018-07-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Deerfield TB-14 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-01-29 | 2020-10-08 | [5 empty] | 7700000 | 4779000 | 4779000 | 5300000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000 | 5466000
Asset Condition | 1a | 52 | NH | Eversource |  |  | 2018-11-01 | Eversource Energy Autotransformer Replacement Plan | Replace the Littleton TB-41 autotransformer and bus upgrades to accommodate new transformer specifications | [5 empty] | Proposed | Proposed | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-01-29 | NR | [5 empty] | 6200000 | 3891000 | 3891000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000 | 4331000
Asset Condition | 1a | 53 | MA | National Grid, USA |  |  | 2024-06-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 2 | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [6 empty] | 12353000 | 12353000 | 11353000 | 11353000 | 11353000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 13044000 | 17732000 | 17732000 | 17732000 | 17732000 | 17732000 | 17732000
Asset Condition | 1a | 54 | RI | National Grid, USA |  |  | 2019-12-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | NR | [6 empty] | 427000 | 427000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1122000 | 1174157 | 1174157 | 1174157 | 1174157 | 1174157 | 1174157 | 1174157
Asset Condition | 1a | 55 | NH | Eversource |  |  | 2018-07-01 |  | 345 kV Structure Replacement Project - Line 307 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 12900000 | 12900000 | 12900000 | 12900000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000 | 11154000
Asset Condition | 1a | 56 | NH | Eversource |  |  | 2018-08-05 |  | 345 kV Structure Replacement Project - Line 326 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 12300000 | 12300000 | 12300000 | 12300000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000 | 11702000
Asset Condition | 1a | 57 | NH | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 367 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 15800000 | 15800000 | 15800000 | 15800000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000 | 15235000
Asset Condition | 1a | 58 | NH | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 379 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 14800000 | 14800000 | 14800000 | 14800000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000 | 14453000
Asset Condition | 1a | 59 | NH | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 381 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13600000 | 13600000 | 13600000 | 13600000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000 | 16255000
Asset Condition | 1a | 60 | NH | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 391 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 19600000 | 19600000 | 19600000 | 19600000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000 | 17858000
Asset Condition | 1a | 61 | MA | Eversource |  |  | 2017-09-01 |  | 1231/1242 Structure Replacement Project | [6 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-02-15 | [6 empty] | 7966000 | 7966000 | 7966000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000 | 10860000
Asset Condition | 1a | 62 | MA | Eversource |  |  | 2018-12-01 |  | Oil Circuit Breaker Replacement Project at the Agawam Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [6 empty] | 5400000 | 5400000 | 5400000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000 | 4700000
Asset Condition | 1a | 63 | MA | Eversource |  |  | 2023-12-01 |  | Lexington Station #320 Asset Condition Upgrade Project | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2020-07-01 | [6 empty] | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 14300000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000 | 16612000
Asset Condition | 1a | 64 | MA | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Project - Line 393 | [6 empty] | Proposed | Proposed | Proposed | In-service | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2019-12-16 | [6 empty] | 10000000 | 10000000 | 10000000 | 10000000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000 | 17190000
Asset Condition | 1a | 65 | MA | Eversource |  |  | 2020-06-01 |  | Laminated Structure Replacement Project - Line 1512 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 14500000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000 | 15100000
Asset Condition | 1a | 66 | MA | Eversource |  |  | 2019-05-01 |  | Laminated Structure Replacement Project - Line 1211/1161 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 12500000 | 12500000 | 12500000 | 12500000 | 12500000 | 12598500 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000 | 12985000
Asset Condition | 1a | 67 | CT | Eversource |  |  | 2022-05-01 |  | Manchester Control House Expansion | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | NR | 2020-10-08 | [6 empty] | 21400000 | 21400000 | 21400000 | 21400000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000 | 48322000
Asset Condition | 1a | 68 | CT | Eversource |  |  | 2019-04-01 |  | Card-Montville-Tunnel Corridor Asset Condition and OPGW Installation Project | [6 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-10-16 | [6 empty] | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000 | 54964000
Asset Condition | 1a | 69 | CT | Eversource |  |  | 2018-12-01 |  | Oil Circuit Breaker Replacement Project at the Frost Bridge Substation | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2018-08-24 | [6 empty] | 7250000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000 | 6353000
Asset Condition | 1a | 70 | CT | Eversource |  |  | 2020-04-01 |  | Oil Circuit Breaker Replacement Project at the Plumtree Substation | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-12-22 | [6 empty] | 6900000 | 6900000 | 6900000 | 6900000 | 6900000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000 | 5868000
Asset Condition | 1a | 71 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 310 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 16500000 | 16500000 | 16500000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000 | 14994000
Asset Condition | 1a | 72 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 321 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/16/2019 2/19/202 | [6 empty] | 6000000 | 6000000 | 6000000 | 5847000 | 5847000 | 5847000 | 5847000 | 5847000 | 5847000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000 | 7462000
Asset Condition | 1a | 73 | CT | Eversource |  |  | 2018-11-01 |  | 345 kV Structure Replacement Project - Line 330 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13500000 | 13500000 | 13500000 | 13500000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000 | 13695000
Asset Condition | 1a | 74 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 348 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 16000000 | 16000000 | 16000000 | 16000000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000 | 19393000
Asset Condition | 1a | 75 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 364 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 14300000 | 14300000 | 14300000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000 | 14220000
Asset Condition | 1a | 76 | CT | Eversource |  |  | 2020-05-01 |  | 345 kV Structure Replacement Project - Line 371 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 12/16/2019 2/19/2020 | [6 empty] | 10600000 | 10600000 | 10600000 | 11546000 | 11546000 | 11546000 | 11546000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000 | 12807000
Asset Condition | 1a | 77 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 383 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 15500000 | 15500000 | 15500000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000 | 13492000
Asset Condition | 1a | 78 | CT | Eversource |  |  | 2018-12-01 |  | 345 kV Structure Replacement Project - Line 387 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 13100000 | 13100000 | 13100000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000 | 13771000
Asset Condition | 1a | 79 | CT | Eversource |  |  | 2018-05-01 |  | 345 kV Structure Replacement Project - Line 398 | [6 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 7800000 | 7800000 | 7800000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000 | 9594000
Asset Condition | 1a | 80 | CT | Eversource |  |  | 2018-07-01 |  | 345 kV Structure Replacement Project - Line 3041 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 9700000 | 9700000 | 9700000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000 | 8276000
Asset Condition | 1a | 81 | CT | Eversource |  |  | 2018-09-01 |  | 345 kV Structure Replacement Project - Line 3642 | [6 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-12-16 | [6 empty] | 9900000 | 9900000 | 9900000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000 | 10151000
Asset Condition | 1a | 82 | CT | Eversource |  |  | 2020-05-01 |  | Laminated Structure Replacement Project - Line 1505/1607 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000 | 52500000
Asset Condition | 1a | 83 | CT | Eversource |  |  | 2020-05-01 |  | Laminated Structure Replacement Project - Line 1675/1080 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 17800000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000 | 18132000
Asset Condition | 1a | 84 | CT | Eversource |  |  | 2018-12-01 |  | Laminated Structure Replacement Project - Line 1921 | [6 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-20 | [6 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000 | 7887000
Asset Condition | 1a | 85 | NH | New Hampshire Transmission |  |  | 2019-12-01 | Seabrook 345 kV GIS Switchyard Like-for Like Equipment Replacement | Phase 1 of mulit-phase project involving like for like equipment replacement. Phase 1 included replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345kV Seabrook-to-Timberswamp 369 line. Post-top insulators for the 369 line located in the open-air to GIS transition yard were also replaced. A bridge covering the GILs where they go below grade and then resurface upon entering the fenced-in Protected Area where the GIS Switchyard is located was replaced during this phase. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-04-21 | [6 empty] | 77017000 | 77017000 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778 | 87421778
Asset Condition | 1a | 86 | NH | New Hampshire Transmission |  |  | 2020-11-01 | Seabrook 345 kV GIS Switchyard Phase 2 Equipment Replacement Part of Asset Condition #85 | Phase 2 of mulit-phase project involving like for like equipment replacement. Phase 2 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345 kV Seabrook-Scobie Pond 363 line, and replacing two GIS 345 kV Circuit Breakers and related switches that are the 363 line termination equipment. Post-top insulators for the 363 line located in the open-air to GIS transition yard will also be replaced. Phase 2 also includes replacing Breaker Failure Relay Protection Systems for the 363 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 87 | NH | New Hampshire Transmission |  |  | 2022-06-01 | Seabrook 345 kV GIS Switchyard Phase 3 Equipment Replacement Part of Asset Condition #85 | Phase 3 of multi-phase project involving like for like equipment replacement. Phase 3 includes replacing three approximately 1,000 ft. long horizontal gas-insulated lines (GIL) comprising the three phases of the 345 kV Seabrook-Ward Hill 394 line, and replacing two GIS 345 kV Circuit Breakers and related switches that are the 394 line termination equipment. Post-top insulators located in the open-air to GIS transition yard will also be replaced. Phase 3 also includes replacing Breaker Failure Relay Protection Systems for the 394 line. | [6 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | NR | 2019-04-21 | [6 empty] | Part of Project #86 | Part of Project #86 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85 | Part of Project #85
Asset Condition | 1a | 88 | MA | National Grid, USA |  |  | 2019-12-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 1 | [6 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [6 empty] | 1384000 | 1384000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2364000 | 2908881 | 2908881 | 2908881 | 2908881 | 2908881 | 2908881 | 2908881
Asset Condition | 1a | 89 | CT | Eversource |  |  | 2020-06-01 |  | Montville 16X Transformer Replacement | [7 empty] | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2018-05-16 | NR | [7 empty] | 6300000 | 6300000 | 6300000 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676 | 4342676
Asset Condition | 1a | 90 | MA | Eversource |  |  | 2024-12-01 |  | Canal Station #980 BPS and Asset Condition Upgrade Project | [8 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2020-06-30 | [8 empty] | 17923000 | 17923000 | 17923000 | 17923000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 17925000 | 41237000
Asset Condition | 1a | 91 | CT | United Illuminating Company |  |  | 2025-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809A-2 Line (Pequonnock-Congress) | [8 empty] | Proposed | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [8 empty] | 376300000 |  | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 92 | MA | National Grid, USA |  |  | 2022-08-01 |  | Robinson Avenue Station #102 Asset Condition Upgrades | [8 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | NR | 1/29/2021 10/31/2022 | [8 empty] | 8300000 | 8300000 | 8300000 | 8300000 | 10340000 | 10340000 | 10340000 | 10430000 | 10430000 | 14892000 | 14892000 | 18020000 | 18020000 | 18020000 | 18020000 | 18020000
Asset Condition | 1a | 93 | VT | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No
Asset Condition | 1b | 94 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 95 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 96 | MA | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 97 | NH | National Grid, USA |  |  | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 3 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1b | 98 | RI | Rhode Island Energy |  | 2 | 2025-09-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 5 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | NR | No
Asset Condition | 1b | 99 | RI | Rhode Island Energy |  |  | 2025-08-01 | NPCC Directory #1 Protection Modifications | NPCC Directory #1 Protection Modifications - Phase 4 | [8 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | NR | No
Asset Condition | 1a | 100 | NH | Eversource |  |  | 2020-01-01 |  | 115 kV Structure Replacement Project - Line A126 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 8300000 | 8300000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000 | 8292000
Asset Condition | 1a | 101 | NH | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line H123 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 6000000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000 | 6168000
Asset Condition | 1a | 102 | NH | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line H141 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 7700000 | 7700000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000 | 9400000
Asset Condition | 1a | 103 | NH | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line K174 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 8700000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000 | 8665000
Asset Condition | 1a | 104 | NH | Eversource |  |  | 2021-02-01 |  | 115 kV Structure Replacement Project - Line L163 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 14000000 | 14000000 | 14000000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000 | 16992000
Asset Condition | 1a | 105 | NH | Eversource |  |  | 2020-09-01 |  | 115 kV Structure Replacement Project - Line A152 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-02-02 | [9 empty] | 6100000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000 | 6884000
Asset Condition | 1b | 106 | NH | Eversource |  |  | 2023-12-11 |  | 115 kV Structure Replacement Project - Line X178 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000 | 11200000
Asset Condition | 1a | 107 | MA | Eversource |  |  | 2021-06-01 |  | 349X/Y 345 kV Cable Replacement | [9 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2019-10-07 | 2020-06-30 | [9 empty] | 72400000 | 72400000 | 72400000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000 | 72430000
Asset Condition | 1a | 108 | MA | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 65-508 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 19500000 | 19500000 | 19500000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000 | 14043000
Asset Condition | 1a | 109 | MA | Eversource |  |  | 2019-03-01 |  | 115 kV Structure Replacement Project - Line 1327 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 7800000 | 7800000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000 | 3774000
Asset Condition | 1a | 110 | MA | Eversource |  |  | 2019-03-01 |  | 115 kV Structure Replacement Project - Line 1428 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12100000 | 12100000 | 12100000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000 | 7487000
Asset Condition | 1a | 111 | MA | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1447 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 6600000 | 6600000 | 6600000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000 | 4332000
Asset Condition | 1a | 112 | MA | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line 1962 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 20300000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000 | 4400000
Asset Condition | 1a | 113 | MA | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1768-MA | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-18 | [9 empty] | 3000000 | 3000000 | 3000000 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142 | Part of Asset Condition #142
Asset Condition | 1a | 114 | MA | Eversource |  |  | 2019-11-01 |  | 115 kV Structure Replacement Project - Line F132 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 11000000 | 11000000 | 11000000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000 | 14772000
Asset Condition | 1a | 115 | CT | Eversource |  |  | 2019-09-01 |  | 1608 115 kV Line Cable Replacement | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | 2019-12-19 | 2020-04-28 | [9 empty] | 11300000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000 | 8182000
Asset Condition | 1a | 116 | CT | Eversource |  |  | 2019-01-01 |  | 1880 115 kV Line Cable Replacement | [9 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2020-04-28 | [9 empty] | 7200000 | 7200000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000 | 6959000
Asset Condition | 1a | 117 | CT | Eversource |  |  | 2019-05-01 |  | 115 kV Structure Replacement Project - Line 1050 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7300000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000 | 7230000
Asset Condition | 1b | 118 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1191 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000 | 8300000
Asset Condition | 1a | 119 | CT | Eversource |  |  | 2019-06-01 |  | 115 kV Structure Replacement Project - Line 1256 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12200000 | 12200000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000 | 9959000
Asset Condition | 1a | 120 | CT | Eversource |  |  | 2020-10-01 |  | 115 kV Structure Replacement Project - Line 1261/1598 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2/19/2021 5/31/2022 | [9 empty] | 18300000 | 18300000 | 18300000 | 20352000 | 20352000 | 20352000 | 20352000 | 20352000 | 20352000 | 23854000 | 23854000 | 23854000 | 23854000 | 23854000 | 23854000
Asset Condition | 1b | 121 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1280 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000 | 7500000
Asset Condition | 1a | 122 | CT | Eversource |  |  | 2021-03-01 |  | 115 kV Structure Replacement Project - Line 1310 | [9 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8300000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000 | 8299000
Asset Condition | 1b | 123 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1410 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
Asset Condition | 1a | 124 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Structure Replacement Project - Line 1448 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 6900000 | 6926000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000 | 6928000
Asset Condition | 1a | 125 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1565 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 11500000 | 11500000 | 11500000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000 | 9095000
Asset Condition | 1a | 126 | CT | Eversource |  |  | 2019-04-01 |  | 115 kV Structure Replacement Project - Line 1620 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 10000000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000 | 9993000
Asset Condition | 1a | 127 | CT | Eversource |  |  | 2021-02-01 |  | 115 kV Structure Replacement Project - Line 1635 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5700000 | 5764000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000 | 5608000
Asset Condition | 1a | 128 | CT | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Project - Line 1675 | [9 empty] | Proposed | Under Construction | Cancelleed | Cancelleed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000 | 7300000
Asset Condition | 1a | 129 | CT | Eversource |  |  | 2020-08-01 |  | 115 kV Structure Replacement Project - Line 1726 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 16300000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000 | 16272000
Asset Condition | 1a | 130 | CT | Eversource |  |  | 2021-12-01 |  | 115 kV Structure Replacement Project - Line 1465 | [9 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7000000 | 7000000 | 7000000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000 | 7743000
Asset Condition | 1a | 131 | CT | Eversource |  |  | 2018-11-01 |  | 115 kV Structure Replacement Project - Line 1751 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [9 empty] | 12500000 | 12500000 | 12500000 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | Part of Asset Condition #226 | 4467000 | 4467000 | 4467000 | 4467000 | 4467000 | 4467000 | 4467000
Asset Condition | 1b | 132 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Structure Replacement Project - Line 1756 | [9 empty] | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [9 empty] | 7000000 | 7000000 | 7000000 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227 | Part of Asset Condition #227
Asset Condition | 1a | 133 | CT | Eversource |  |  | 2018-09-01 |  | 115 kV Structure Replacement Project - Line 1759 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 7300000 | 7300000 | 7300000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000 | 6076000
Asset Condition | 1a | 134 | CT | Eversource |  |  | 2020-11-01 |  | 115 kV Structure Replacement Project - Line 1765 | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 12300000 | 12300000 | 12300000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000 | 13122000
Asset Condition | 1a | 135 | CT | Eversource |  |  | 2018-06-01 |  | 115 kV Structure Replacement Project - Line 1766 | [9 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5800000 | 5800000 | 5800000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000 | 5426000
Asset Condition | 1a | 136 | CT | Eversource |  |  | 2018-04-01 |  | 115 kV Structure Replacement Project - Line 1767 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5400000 | 5400000 | 5400000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000 | 5250000
Asset Condition | 1a | 137 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1769 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8200000 | 8200000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000 | 8247000
Asset Condition | 1a | 138 | CT | Eversource |  |  | 2018-10-01 |  | 115 kV Structure Replacement Project - Line 1770 (the 1770 line has been replaced by the Plumtree to Stony Hill 1268 line and the Stony Hill to Bates Rock 1485 line) | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 16300000 | 16300000 | 16300000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000 | 8811000
Asset Condition | 1a | 139 | CT | Eversource |  |  | 2021-08-07 |  | 115 kV Structure Replacement Project - Line 1772 | [9 empty] | In-service | In-service | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 10000000 | 10000000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000 | 10328000
Asset Condition | 1a | 140 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1783 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 8200000 | 8200000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000 | 8113000
Asset Condition | 1a | 141 | CT | Eversource |  |  | 2019-10-01 |  | 115 kV Structure Replacement Project - Line 1785 | [9 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 9000000 | 9000000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000 | 8968000
Asset Condition | 1a | 142 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1768-CT | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5200000 | 5200000 | 5200000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000 | 7586000
Asset Condition | 1a | 143 | CT | Eversource |  |  | 2018-12-01 |  | 115 kV Structure Replacement Project - Line 1910 | [9 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [9 empty] | 5800000 | 5800000 | 5800000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000 | 5780000
Asset Condition | 1a | 144 | CT | Eversource |  |  | 2021-10-01 |  | Millstone Substation 15G High Creep Insulator Replacement | [9 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2020-10-08 | [9 empty] | 11500000 | 11500000 | 11500000 | 11500000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000 | 16597000
Asset Condition | 1a | 145 | MA | National Grid, USA |  |  | 2024-05-01 |  | Carpenter Hill Control House Rebuild | [9 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-04-11 | [9 empty] | 6860000 | 6860000 | 6860000 | 6860000 | 6860000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000 | 14485000
Asset Condition | 1a | 146 | MA | National Grid, USA |  |  | 2024-05-01 |  | 327 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [9 empty] | 60400000 | 60400000 | 60400000 | 60400000 | 60400000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000 | 87877000
Asset Condition | 1a | 147 | MA | National Grid, USA |  |  | 2022-02-01 |  | 303 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-31 | [9 empty] | 24700000 | 24700000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000 | 22472000
Asset Condition | 1a | 148 | MA | National Grid, USA |  |  | 2020-05-01 |  | 3520 Line Asset Condition Refurbishments | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-31 | [9 empty] | 6900000 | 6900000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000 | 5618000
Asset Condition | 1a | 149 | MA | National Grid, USA |  |  | 2024-12-01 |  | 315 Line Asset Condition Refurbishments - MA Portion | [9 empty] | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [9 empty] | 53500000 | 53500000 | 53500000 | 53500000 | 53500000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000 | 99072000
Asset Condition | 1a | 150 | RI | Rhode Island Energy |  |  | 2025-06-01 |  | 315 Line Asset Condition Refurbishments - RI Portion | [9 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | NR | 2021-01-29 | [9 empty] | 16500000 | 16500000 | 16500000 | 16500000 | 16500000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000 | 25107000
Asset Condition | 1a | 151 | CT | United Illuminating Company |  |  | 2025-01-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8809B-2 Line (Pequonnock - Congress) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320 | 17422320
Asset Condition | 1a | 152 | CT | United Illuminating Company |  |  | 2028-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild portion of 1130 Line (Pequonnock - UI Str. B737) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614 | 21493614
Asset Condition | 1a | 153 | CT | United Illuminating Company |  |  | 2028-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 1430 Line (Ash Creek - ESE Str. B648) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220 | 71391220
Asset Condition | 1a | 154 | CT | United Illuminating Company |  |  | 2026-08-08 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 91001-1 Line (Pequonnock - Bridgeport Resco) & 91001-2 Line (Bridgeport Resco - Ash Creek) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | No | [10 empty] | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324 | 51963324
Asset Condition | 1a | 155 | CT | United Illuminating Company |  |  | 2026-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005A-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 69080000 | 69080000 | 69080000
Asset Condition | 1a | 156 | CT | United Illuminating Company |  |  | 2026-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88005B-1 Line (Milvon - Woodmont) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 40124764 | 69080000 | 69080000 | 69080000
Asset Condition | 1a | 157 | CT | United Illuminating Company |  |  | 2027-11-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804A Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 51810000 | 51810000 | 51810000
Asset Condition | 1a | 158 | CT | United Illuminating Company |  |  | 2027-11-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 8804B Line (Woodmont - Allings Crossing) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 28940339 | 51810000 | 51810000 | 51810000
Asset Condition | 1a | 159 | CT | United Illuminating Company |  |  | 2025-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 25905000 | 25905000 | 25905000
Asset Condition | 1a | 160 | CT | United Illuminating Company |  |  | 2025-04-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-3 Line (Allings Crossing - Elmwest) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 14700532 | 25905000 | 25905000 | 25905000
Asset Condition | 1a | 161 | CT | United Illuminating Company |  |  | 2024-10-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003A-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 25905000 | 25905000 | 25905000
Asset Condition | 1a | 162 | CT | United Illuminating Company |  |  | 2024-10-01 | Railroad Corridor Transmission Line Asset Condition Upgrades | Rebuild 88003B-2 Line (Elmwest - West River) | [9 empty] | Concept | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2019-01-28 | 2023-09-12 | [10 empty] | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 14544175 | 25905000 | 25905000 | 25905000
Asset Condition | 1a | 163 | CT | Eversource |  |  | 2020-12-01 |  | 667 69 kV line rebuild and asset condition project | [10 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 7/25/2019 8/28/2020 | 2020-04-28 | [10 empty] | 24080000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000 | 24079000
Asset Condition | 1a | 164 | CT | Eversource |  |  | 2022-03-01 |  | 345 kV Structure Replacement Projects - Line 310 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 19900000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000 | 19740000
Asset Condition | 1a | 165 | CT | Eversource |  |  | 2019-12-01 |  | 345 kV Structure Replacement Projects - Line 321 | [11 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 6500000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000 | 6481000
Asset Condition | 1a | 166 | CT | Eversource |  |  | 2021-11-01 |  | 345 kV Structure Replacement Projects - Line 330 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000 | 17126000
Asset Condition | 1a | 167 | CT | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Projects - Line 348 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 19400000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000 | 15110000
Asset Condition | 1a | 168 | CT | Eversource |  |  | 2020-06-01 |  | 345 kV Structure Replacement Projects - Line 352 | [11 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 12500000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000 | 12842000
Asset Condition | 1a | 169 | CT | Eversource |  |  | 2019-08-07 |  | 345 kV Structure Replacement Projects - Line 362 | [11 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000 | 5088000
Asset Condition | 1a | 170 | CT | Eversource |  |  | 2022-07-01 |  | 345 kV Structure Replacement Projects - Line 364 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 17300000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000 | 16355000
Asset Condition | 1a | 171 | CT | Eversource |  |  | 2019-12-01 |  | 345 kV Structure Replacement Projects - Line 368 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 7300000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000 | 7077000
Asset Condition | 1a | 172 | CT | Eversource |  |  | 2022-03-01 |  | 345 kV Structure Replacement Projects - Line 383 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-01 | [11 empty] | 22200000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000 | 22083000
Asset Condition | 1a | 173 | CT | Eversource |  |  | 2021-11-01 |  | 345 kV Structure Replacement Projects - Line 387 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-01 | [11 empty] | 18200000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000 | 18090000
Asset Condition | 1a | 174 | CT | Eversource |  |  | 2019-07-01 |  | 345 kV Structure Replacement Projects - Line 3041 | [11 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000 | 9737000
Asset Condition | 1a | 175 | CT | Eversource |  |  | 2019-10-01 |  | 345 kV Structure Replacement Projects - Line 3252 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000 | 7523000
Asset Condition | 1a | 176 | CT | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | NR | 2021-02-01 | [11 empty] | 11900000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000 | 11131000
Asset Condition | 1a | 177 | CT | Eversource |  |  | 2019-07-01 |  | 345 kV Structure Replacement Projects - Line 3424 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 7900000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000 | 7663000
Asset Condition | 1a | 178 | CT | Eversource |  |  | 2024-03-01 |  | 345 kV Structure Replacement Projects - Line 3754 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | No | [11 empty] | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000 | 8200000
Asset Condition | 1a | 179 | MA | Eversource |  |  | 2019-10-01 |  | 345 kV Structure Replacement Projects - Line 336 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 6600000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000 | 6021000
Asset Condition | 1a | 180 | MA | Eversource |  |  | 2019-08-01 |  | 345 kV Structure Replacement Projects - Line 3361 | [11 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [11 empty] | 6300000 | 6300000 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951 | 4992951
Asset Condition | 1a | 181 | MA | Eversource |  |  | 2022-08-01 |  | 345 kV Structure Replacement Projects - Line 312 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000 | 41300000
Asset Condition | 1a | 182 | MA | Eversource |  |  | 2019-11-01 |  | 345 kV Structure Replacement Projects - Line 354 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 29600000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000 | 20900000
Asset Condition | 1a | 183 | MA | Eversource |  |  | 2019-09-01 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 12500000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000 | 12358000
Asset Condition | 1a | 184 | MA | Eversource |  |  | 2021-03-01 |  | 345 kV Structure Replacement Project - Line 393 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 11000000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000 | 9842000
Asset Condition | 1a | 185 | MA | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 3419 | [11 empty] | Proposed | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 26000000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000 | 26175000
Asset Condition | 1a | 186 | NH | Eversource |  |  | 2020-03-01 |  | 345 kV Structure Replacement Projects - Line 326 | [11 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [11 empty] | 5200000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000 | 3630000
Asset Condition | 1a | 187 | NH | Eversource |  |  | 2021-02-01 |  | 345 kV Structure Replacement Projects - Line 367 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 14100000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000 | 13631000
Asset Condition | 1a | 188 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 373 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 10300000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000 | 10995000
Asset Condition | 1a | 189 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 379 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 9700000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000 | 11589000
Asset Condition | 1a | 190 | NH | Eversource |  |  | 2020-01-01 |  | 345 kV Structure Replacement Projects - Line 381 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 8300000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000 | 6590000
Asset Condition | 1a | 191 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 385 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 14000000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000 | 14408000
Asset Condition | 1a | 192 | NH | Eversource |  |  | 2020-12-01 |  | 345 kV Structure Replacement Projects - Line 391 | [11 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [11 empty] | 16400000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000 | 17313000
Asset Condition | 1a | 193 | CT | Eversource |  |  | 2019-12-01 |  | 115 kV Structure Replacement Projects - Line 1470 | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [11 empty] | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000 | 11111000
Asset Condition | 1a | 194 | MA | Eversource |  |  | 2023-12-01 |  | 110-510 & 110-511 lines 115 kV HPFF refurbishment | [11 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2020-04-29 | 2022-06-03 | [11 empty] | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 95000000 | 97995000 | 97995000 | 97995000 | 97995000 | 97995000 | 97995000 | 97995000
Asset Condition | 1a | 195 | VT | Vermont Electric Power Company |  |  | 2021-07-01 |  | Sand Bar Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers, switches | [11 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-19 | [11 empty] | 10600000 | 10600000 | 10600000 | 10600000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000 | 10640000
Asset Condition | 1a | 196 | VT | Vermont Electric Power Company |  |  | 2020-12-01 |  | Berlin Substation - Mitigate several Asset Condition concerns: Control House, P&C, circuit breakers & switches. Install a second protection system. | [11 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-01 | [11 empty] | 5872719 | 5550000 | 5550000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000 | 6600000
Asset Condition | 1a | 197 | CT | United Illuminating Company |  |  | 2019-10-01 |  | 1130 Line Optical Ground Wire (OPGW) Replacement | [11 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2019-10-30 | [11 empty] | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000 | 8170000
Asset Condition | 1a | 198 | NH | Eversource |  |  | 2020-09-01 |  | 115 kV Wood Pole Replacement - B143 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 7410000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000 | 6403000
Asset Condition | 1a | 199 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole Replacement - C129 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2/2/2021 6/3/2022 | [12 empty] | 9100000 | 9045000 | 9045000 | 9045000 | 9045000 | 9045000 | 10048000 | 10048000 | 10048000 | 10048000 | 10048000 | 10048000
Asset Condition | 1a | 200 | NH | Eversource |  |  | 2021-06-01 |  | 115 kV Wood Pole Replacement - F139 | [12 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 8000000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000 | 7530000
Asset Condition | 1a | 201 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole Replacement - G128 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 6910000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000 | 7404000
Asset Condition | 1a | 202 | NH | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole Replacement - K105 | [12 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [12 empty] | 6080000 | 6080000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000 | 4100000
Asset Condition | 1a | 203 | NH | Eversource |  |  | 2022-04-01 |  | 115 kV Wood Pole and Shield Wire Replacement - K174 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 14740000 | 14740000 | 14740000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000 | 16240000
Asset Condition | 1a | 204 | NH | Eversource |  |  | 2020-03-01 |  | 115 kV Wood Pole Replacement - L175 | [12 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | NR | [12 empty] | 5250000 | 5250000 | 5250000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000 | 3809000
Asset Condition | 1a | 205 | NH | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - M127 | [12 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 33430000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000 | 29740000
Asset Condition | 1a | 206 | NH | Eversource |  |  | 2020-11-01 |  | 115 kV Wood Pole and Shield Wire Replacement - Y138 | [12 empty] | Proposed | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 8490000 | 8490000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000 | 8475000
Asset Condition | 1a | 207 | MA | Eversource |  |  | 2021-10-01 |  | 115 kV Wood Pole Replacement - 1161 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2/2/2021 12/23/2022 | [12 empty] | 17100000 | 17100000 | 17100000 | 22578000 | 22578000 | 22578000 | 22578000 | 22578000 | 24992000 | 24992000 | 24992000 | 24992000
Asset Condition | 1a | 208 | MA | Eversource |  |  | 2022-09-01 |  | 115 kV Wood Pole Replacement - 1421 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 15750000 | 15750000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000 | 22656000
Asset Condition | 1a | 209 | MA | Eversource |  |  | 2020-10-01 |  | 115 kV Wood Pole Replacement - 1512 | [12 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000 | 10800000
Asset Condition | 1a | 210 | MA | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1394 | [12 empty] | Proposed | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 7070000 | 7070000 | 7070000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000 | 8877000
Asset Condition | 1a | 211 | MA | Eversource |  |  | 2020-07-01 |  | 115 kV Wood Pole and Shield Wire Replacement - Line 1858 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000 | 11340000
Asset Condition | 1a | 212 | MA | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1976 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-02-02 | [12 empty] | 7470000 | 7470000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000 | 9688000
Asset Condition | 1a | 213 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1000 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | 2023-06-05 | [12 empty] | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 12400000 | 13690000 | 13690000
Asset Condition | 1a | 214 | CT | Eversource |  |  | 2021-03-01 |  | 115 kV Wood Pole Replacement - 1042 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 6080000 | 6080000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000 | 8273000
Asset Condition | 1a | 215 | CT | Eversource |  |  | 2020-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1043 | [12 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000 | 5394000
Asset Condition | 1a | 216 | CT | Eversource |  |  | 2024-06-01 |  | 115 kV Wood Pole Replacement - 1080 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | NR | 2023-06-05 | [12 empty] | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 24180000 | 23574000 | 23574000 | 23574000
Asset Condition | 1a | 217 | CT | Eversource |  |  | 2021-08-01 |  | 115 kV Wood Pole Replacement - 1208 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 8960000 | 8960000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000 | 9577000
Asset Condition | 1a | 218 | CT | Eversource |  |  | 2021-10-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1232 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | NR | [12 empty] | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 6700000 | 2422000 | 2422000 | 2422000 | 2422000 | 2422000 | 2422000
Asset Condition | 1a | 219 | CT | Eversource |  |  | 2022-08-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1256 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 10640000 | 10640000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000 | 14826000
Asset Condition | 1a | 220 | CT | Eversource |  |  | 2023-08-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1280 Line | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | 2023-06-05 | [12 empty] | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 12000000 | 13956000 | 19726000 | 19726000 | 19726000
Asset Condition | 1a | 221 | CT | Eversource |  |  | 2022-09-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1410 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 13000000 | 13000000 | 13000000 | 10091000 | 10091000 | 10091000 | 10091000 | 8353000 | 8353000 | 8353000 | 8353000 | 8353000
Asset Condition | 1a | 222 | CT | Eversource |  |  | 2020-06-01 |  | 115 kV Wood Pole Replacement - Line 1505 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000 | 7100000
Asset Condition | 1a | 223 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Wood Pole Replacement - 1607 | [12 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000 | 7626000
Asset Condition | 1a | 224 | CT | Eversource |  |  | 2022-05-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1618 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | 2020-08-28 | 2023-06-05 | [12 empty] | 9770000 | 9770000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000 | 8767000
Asset Condition | 1a | 225 | CT | Eversource |  |  | 2022-12-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1732 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 7900000 | 7900000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000 | 13877000
Asset Condition | 1b | 226 | CT | Eversource |  |  | 2023-12-11 |  | 115 kV Wood Pole Replacement - 1751 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled | NR | No | [12 empty] | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000 | 10750000
Asset Condition | 1a | 227 | CT | Eversource |  |  | 2021-11-01 |  | 115 kV Wood Pole Replacement - 1756 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 15000000 | 15000000 | 15000000 | 15000000 | 15000000 | 24469000 | 24469000 | 24469000 | 24469000 | 24469000 | 24469000 | 24469000
Asset Condition | 1a | 228 | CT | Eversource |  |  | 2021-04-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1765 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | NR | [12 empty] | 14700000 | 14700000 | 8801000 | 8801000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000 | 3800000
Asset Condition | 1a | 229 | CT | Eversource |  |  | 2021-02-01 |  | 115 kV Wood Pole and Shield Wire Replacement - 1766 | [12 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 16600000 | 16600000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000 | 16556000
Asset Condition | 1a | 230 | CT | Eversource |  |  | 2022-06-01 |  | 115 kV Wood Pole Replacement - 1910 | [12 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [12 empty] | 10300000 | 10300000 | 10300000 | 10300000 | 10300000 | 10300000 | 8226000 | 8226000 | 8226000 | 8226000 | 8226000 | 8226000
Asset Condition | 1a | 231 | CT | Eversource |  |  | 2020-04-01 |  | 115 kV Line Rebuild and Asset Condition Project - Line 1355 | [12 empty] | Proposed | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2021-02-19 | [12 empty] | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000 | 7450000
Asset Condition | 1a | 232 | VT | Vermont Electric Power Company |  |  | 2025-12-01 |  | Line 340 Asset Condition Structure Refurbishment | [13 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-01-29 | [13 empty] | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000 | 37200000
Asset Condition | 1a | 233 | VT | Vermont Electric Power Company |  |  | 2020-12-01 |  | Line K41 Asset Condition Structure Refurbishment | [13 empty] | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-01-29 | [13 empty] | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000 | 9300000
Asset Condition | 1b | 234 | MA | National Grid, USA |  |  | 2026-10-01 |  | Chestnut Hill #702 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Cancelled | Cancelled | Cancelled | Cancelled | No | No
Asset Condition | 1a | 235 | VT | National Grid, USA |  |  | 2025-07-01 |  | Vernon #13 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | 2022-07-20 | No | [19 empty] | 39690000 | 39690000 | 39690000 | 39690000 | 39690000
Asset Condition | 1b | 236 | MA | National Grid, USA |  |  | 2028-11-01 |  | Deerfield #4 Substation Asset Replacements | [13 empty] | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | Concept | No | No
Asset Condition | 1a | 237 | MA | National Grid, USA |  |  | 2029-12-01 |  | A-1 & B-2 69 kV Line Asset Condition Project | [13 empty] | Concept | Concept | Concept | Concept | Proposed | Planned | Planned | Planned | Planned | Planned | Planned | 2020-06-02 | No | [17 empty] | 347300000 | 347300000 | 347300000 | 325430000 | 325430000 | 325430000 | 325430000
Asset Condition | 1a | 238 | MA | Eversource |  |  | 2020-06-01 |  | 115 kV Granville Junction to Atwater 1853 line (formerly 1512) OPGW Project | [13 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | NR | [13 empty] | 5000000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000 | 4800000
Asset Condition | 1a | 239 | CT | United Illuminating Company |  |  | 2025-01-01 |  | Derby Junction to Ansonia Corridor 115 kV Transmission Upgrades | [13 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Planned | Planned | Planned | Planned | NR | No | [13 empty] | 22374000 | 22374000 | 22374000 | 22374000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 36000000 | 70986666
Asset Condition | 1a | 240 | MA | National Grid, USA |  |  | 2022-10-01 | Boston 2028 Project | Rebuild the Golden Hills #90 Substation | [14 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-04-08 | [14 empty] | 9345000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000 | 10180000
Asset Condition | 1a | 241 | CT | Eversource |  |  | 2021-05-01 |  | Glenbrook STATCOM Replacement | [14 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2021-04-14 | 8/21/2021 12/23/2022 | [14 empty] | 21600000 | 21624000 | 18699000 | 18699000 | 18699000 | 18699000 | 21298000 | 21298000 | 21298000 | 21298000
Asset Condition | 1a | 242 | CT | Eversource |  |  | 2021-08-07 |  | Horton Cove Asset Condition and OPGW Project | [14 empty] | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2020-11-06 | 2022-06-01 | [14 empty] | 13400000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000 | 13949000
Asset Condition | 1a | 243 | CT | Eversource |  |  | 2021-06-01 |  | 115 kV Lattice Tower Asset Condition and OPGW Project - Line 1768 | [14 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2020-11-06 | 2021-08-21 | [14 empty] | 22600000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000 | 22929000
Asset Condition | 1a | 244 | CT | Eversource |  |  | 2021-09-01 |  | 115 kV Copper Conductor and Wood Pole Replacement - Line 1191 | [14 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2020-10-05 | 2021-08-21 | [14 empty] | 38050000 | 38050000 | 38054000 | 38054000 | 38054000 | 38054000 | 38054000 | 38054000 | 38054000 | 38054000
Asset Condition | 1a | 245 | CT | Eversource |  |  | 2022-04-01 |  | Southington Substation Relay Replacement Project | [15 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2021-08-21 | [15 empty] | 9400000 | 9362000 | 9362000 | 9362000 | 9362000 | 9362000 | 9362000 | 9362000 | 9362000
Asset Condition | 1a | 246 | CT | Eversource |  |  | 2018-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 329 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-28 | [15 empty] | 5925000 | 5925000 | 5925000 | 5925000 | 5925000 | 5925000 | 5925000 | 5925000 | 5925000
Asset Condition | 1a | 247 | CT | Eversource |  |  | 2018-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 352 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-28 | [15 empty] | 5998000 | 5998000 | 5998000 | 5998000 | 5998000 | 5998000 | 5998000 | 5998000 | 5998000
Asset Condition | 1a | 248 | MA | Eversource |  |  | 2017-12-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 338 345 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-28 | [15 empty] | 5804000 | 5804000 | 5804000 | 5804000 | 5804000 | 5804000 | 5804000 | 5804000 | 5804000
Asset Condition | 1a | 249 | MA | Eversource |  |  | 2019-06-01 |  | Prior Year Wood Structure Asset Condition Replacement - Line 455-507 115 kV | [15 empty] | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-10-28 | [15 empty] | 10296000 | 10296000 | 10296000 | 10296000 | 10296000 | 10296000 | 10296000 | 10296000 | 10296000
Asset Condition | 1a | 250 | MA | Eversource |  |  | 2024-12-11 |  | Copper Conductor and Shield Wire Replacement - Line 1231/1242 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | 2022-10-19 | No | [15 empty] | 97000000 | 97000000 | 97000000 | 97000000 | 97000000 | 158500000 | 158504000 | 158504000 | 158504000
Asset Condition | 1a | 251 | MA | Eversource |  |  | 2022-11-01 |  | 345 kV Line Structure Replacement - Line 312 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 12/23/2022 4/25/2023 | [15 empty] | 19300000 | 19300000 | 21160000 | 21160000 | 21160000 | 21160000 | 26739000 | 26739000 | 26739000
Asset Condition | 1a | 252 | MA | Eversource |  |  | 2021-06-01 |  | 345 kV Line Structure Replacement - Line 319 | [15 empty] | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 7800000 | 7800000 | 7838000 | 7838000 | 7838000 | 7838000 | 7838000 | 7838000 | 7838000
Asset Condition | 1a | 253 | MA | Eversource |  |  | 2021-10-01 |  | 345 kV Line Structure Replacement - Line 338 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000 | 8700000
Asset Condition | 1a | 254 | MA | Eversource |  |  | 2021-04-01 |  | 115 kV Wood Pole Asset Condition Project - Line 455-507 | [15 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-10-27 | [15 empty] | 5191000 | 5191000 | 5191000 | 5191000 | 5191000 | 5191000 | 5191000 | 5191000 | 5191000
Asset Condition | 1b | 255 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1560/1808 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | No | No | [15 empty] | 19700000 | 19700000 | 19700000 | 19700000 | 19700000 | 19700000 | 19700000 | 19700000 | 19700000
Asset Condition | 1b | 256 | CT | Eversource |  |  | 2026-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1580/1142/1808 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Cancelled | Cancelled | No | No | [15 empty] | 68100000 | 68100000 | 68100000 | 68100000 | 68100000 | 68100000 | 68100000 | 68100000 | 68100000
Asset Condition | 1a | 257 | CT | Eversource |  |  | 2021-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1588 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2021-06-17 | No | [15 empty] | 9600000 | 9600000 | 9611000 | 9611000 | 9611000 | 9611000 | 9611000 | 9611000 | 9611000
Asset Condition | 1b | 258 | CT | Eversource |  |  | 2024-06-01 |  | Copper Conductor and Shield Wire Replacement - Line 1268/1485/1622/1887 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [15 empty] | 29600000 | 29600000 | 29600000 | 29600000 | 29600000 | 29600000 | 47200000 | 47200000 | 47200000
Asset Condition | 1b | 259 | CT | Eversource |  |  | 2024-09-01 |  | Copper Conductor and Shield Wire Replacement - Line 1163/1550 | [15 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | 2023-02-23 | No | [15 empty] | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 16700000 | 34500000 | 34500000 | 34486000
Asset Condition | 1a | 260 | CT | Eversource |  |  | 2023-12-01 |  | Copper Conductor and Shield Wire Replacement - Line 1825 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | 2021-12-16 | No | [15 empty] | 7300000 | 7300000 | 7300000 | 7286000 | 7286000 | 7286000 | 7286000 | 7286000 | 7286000
Asset Condition | 1a | 261 | CT | Eversource |  |  | 2022-03-01 |  | 115 kV Wood Pole and Shield Wire Replacement 2020-2023 - Line 1465 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-05 | [15 empty] | 8770000 | 8770000 | 8770000 | 8770000 | 8770000 | 8770000 | 8770000 | 8770000 | 8770000
Asset Condition | 1a | 262 | CT | Eversource |  |  | 2022-10-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 310 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 59200000 | 59200000 | 61333000 | 61333000 | 61333000 | 61333000 | 61333000 | 61333000 | 61333000
Asset Condition | 1a | 263 | CT | Eversource |  |  | 2022-12-01 |  | 345 kV Line Structure Replacement - Line 330 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 12/23/2022 4/25/2023 | [15 empty] | 6600000 | 6600000 | 8039000 | 8039000 | 8039000 | 8039000 | 10248000 | 10248000 | 10248000
Asset Condition | 1a | 264 | CT | Eversource |  |  | 2022-01-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 368 | [15 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 8800000 | 8800000 | 9860000 | 9860000 | 9860000 | 9860000 | 9860000 | 9860000 | 9860000
Asset Condition | 1a | 265 | CT | Eversource |  |  | 2023-02-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 383 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | NR | 2022-12-23 | [15 empty] | 16300000 | 16300000 | 16778000 | 16778000 | 16778000 | 16778000 | 16778000 | 16778000 | 16778000
Asset Condition | 1a | 266 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 387 | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-23 | [15 empty] | 10200000 | 10200000 | 10200000 | 12781000 | 12781000 | 12781000 | 12781000 | 12781000 | 12781000
Asset Condition | 1a | 267 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3041 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-23 | [15 empty] | 14400000 | 14534000 | 14534000 | 14534000 | 14534000 | 14534000 | 14534000 | 14534000 | 14534000
Asset Condition | 1a | 268 | CT | Eversource |  |  | 2023-06-01 |  | 345 kV Line Structure and PINCO insulator Replacement - 3424 Line | [15 empty] | Proposed | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | 2022-12-23 | [15 empty] | 14900000 | 14900000 | 14900000 | 14900000 | 14900000 | 14900000 | 14900000 | 14900000 | 14900000
Asset Condition | 1a | 269 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Line Structure and PINCO insulator Replacement - Line 3754 | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | NR | [15 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 4400000 | 4400000
Asset Condition | 1a | 270 | MA | National Grid, USA |  |  | 2022-06-01 |  | S-145/T-146 115 kV Line Reconductoring - North Reading Substation to Wallace Substation | [15 empty] | Planned | Planned | Planned | Under Construction | Under Construction | In-service | In-service | In-service | In-service | 2020-12-11 | 2022-06-02 | [15 empty] | 16540000 | 16540000 | 16540000 | 16540000 | 16540000 | 21885000 | 21885000 | 21885000 | 21885000
Asset Condition | 1a | 271 | MA | National Grid, USA |  |  | 2023-04-01 |  | V-148S Asset Condition Refurbishment and Switch Replacement - MA Portion | [15 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | Under Construction | In-service | In-service | 2022-03-17 | 2023-01-30 | [15 empty] | 10411000 | 10411000 | 10411000 | 10411000 | 10411000 | 9780000 | 9780000 | 9780000 | 9780000
Asset Condition | 1a | 272 | RI | Rhode Island Energy |  |  | 2022-12-01 |  | V-148S Asset Condition Refurbishment and Switch Replacement - RI Portion | [15 empty] | Proposed | Proposed | Proposed | Proposed | Planned | Under Construction | In-Service | In-service | In-service | 2022-03-17 | 2023-02-07 | [15 empty] | 14322000 | 14322000 | 14322000 | 14322000 | 14322000 | 14590000 | 14580000 | 14580000 | 14580000
Asset Condition | 1a | 273 | NH | Eversource |  |  | 2021-12-01 |  | Copper Conductor and Shield Wire Replacement Projects - C129 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | No | [15 empty] | 18500000 | 12145000 | 12145000 | 12145000 | 12145000 | 12145000 | 12145000 | 12145000 | 12145000
Asset Condition | 1a | 274 | NH | Eversource |  |  | 2022-01-01 |  | Copper Conductor and Shield Wire Replacement Projects - D108 Line | [15 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | In-service | In-service | In-service | 2021-09-22 | No | [15 empty] | 6700000 | 6700000 | 6750000 | 6750000 | 6750000 | 6750000 | 6750000 | 6750000 | 6750000
Asset Condition | 1a | 275 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - G128 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | No | [15 empty] | 7600000 | 5044000 | 5044000 | 5044000 | 5044000 | 5044000 | 5044000 | 5044000 | 5044000
Asset Condition | 1a | 276 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - L163 Line | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | No | [15 empty] | 23300000 | 23310000 | 23310000 | 23310000 | 23310000 | 23310000 | 23310000 | 23310000 | 23310000
Asset Condition | 1a | 277 | NH | Eversource |  |  | 2021-11-01 |  | Copper Conductor and Shield Wire Replacement Projects - X104 | [15 empty] | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | No | [15 empty] | 6994000 | 6994000 | 6994000 | 6994000 | 6994000 | 6994000 | 6994000 | 6994000 | 6994000
Asset Condition | 1a | 278 | NH | Eversource |  |  | 2022-11-01 |  | Amherst substation Protection & Controls Upgrades | [15 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2021-08-21 | [15 empty] | 6100000 | 6100000 | 6100000 | 6100000 | 6081000 | 6081000 | 6081000 | 6081000 | 6081000
Asset Condition | 1a | 279 | NH | Eversource |  |  | 2022-09-01 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - A111 Line | [15 empty] | Proposed | Proposed | Planned | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | 2021-07-15 | 2023-05-31 | [15 empty] | 35940000 | 35940000 | 53501000 | 53501000 | 53501000 | 53501000 | 53501000 | 31227000 | 31227000
Asset Condition | 1a | 280 | NH | Eversource |  |  | 2023-12-11 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - E115 Line | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | Under Construction | Under Construction | Under Construction | Under Construction | 2021-07-15 | 2023-05-31 | [15 empty] | 55116000 | 55116000 | 55116000 | 55116000 | 55116000 | 64147000 | 64147000 | 64147000 | 64147000
Asset Condition | 1a | 281 | NH | Eversource |  |  | 2024-06-01 |  | Webster-Beebe River 115 kV Corridor Asset Condition and OPGW Project - Z180 Line | [15 empty] | Proposed | Proposed | Planned | Planned | Planned | Planned | Planned | Under Construction | Under Construction | 2021-07-15 | 2023-05-31 | [15 empty] | 9669000 | 9669000 | 9669000 | 9669000 | 9669000 | 9669000 | 14529000 | 14529000 | 14529000
Asset Condition | 1a | 282 | NH | Eversource |  |  | 2022-04-01 |  | 345 kV Line Structure Replacements - Line 373 | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [15 empty] | 9351000 | 9351000 | 9351000 | 9351000 | 9351000 | 9351000 | 9351000 | 9351000 | 9351000
Asset Condition | 1a | 283 | VT | Vermont Electric Power Company |  |  | 2022-12-01 |  | Line K22 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2021-08-20 | [15 empty] | 9720000 | 9720000 | 9720000 | 9720000 | 9720000 | 9720000 | 8300000 | 8300000 | 8300000
Asset Condition | 1a | 284 | VT | Vermont Electric Power Company |  |  | 2025-12-01 |  | Line K24 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2021-08-20 | [15 empty] | 15240000 | 15240000 | 15240000 | 15240000 | 15240000 | 15240000 | 15240000 | 15240000 | 15240000
Asset Condition | 1a | 285 | VT | Vermont Electric Power Company |  |  | 2022-12-01 |  | Line K34 Asset Condition Structure Refurbishment | [15 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2021-08-20 | [15 empty] | 6710000 | 6710000 | 6710000 | 6710000 | 6710000 | 6710000 | 7750000 | 7750000 | 7750000
Asset Condition | 1a | 286 | NH | Eversource |  |  | 2021-12-01 |  | Eddy Substation Control House Relocation and Rebuild | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | 2019-07-10 | 2021-08-23 | [16 empty] | 6051000 | 6051000 | 6051000 | 6051000 | 6051000 | 6051000 | 6051000 | 6051000
Asset Condition | 1a | 287 | NH | Eversource |  |  | 2021-11-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - G128 Line | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 12632000 | 12632000 | 12632000 | 12632000 | 12632000 | 12632000 | 12632000 | 12632000
Asset Condition | 1a | 288 | NH | Eversource |  |  | 2021-09-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - L175 Line | [16 empty] | Proposed | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 19300000 | 19300000 | 19300000 | 19300000 | 19300000 | 19300000 | 19300000 | 19300000
Asset Condition | 1a | 289 | NH | Eversource |  |  | 2022-05-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - K105 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 14700000 | 14700000 | 16503000 | 16503000 | 16503000 | 16503000 | 16503000 | 16503000
Asset Condition | 1a | 290 | NH | Eversource |  |  | 2022-12-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - X116 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 26000000 | 26000000 | 24646000 | 24646000 | 24646000 | 24646000 | 24646000 | 24646000
Asset Condition | 1a | 291 | NH | Eversource |  |  | 2022-12-01 |  | NH 115 kV Laminated Wood Structure Replacement Program Phase I - Z119 Line | [16 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-11-01 | [16 empty] | 25400000 | 25400000 | 23443000 | 23443000 | 23443000 | 23443000 | 23443000 | 23443000
Asset Condition | 1a | 292 | CT | Eversource |  |  | 2021-12-01 |  | Branford 11J A3 Bus Replacement Project | [16 empty] | Under Construction | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2021-08-22 | [16 empty] | 10322000 | 10322000 | 10322000 | 10322000 | 10322000 | 10322000 | 10322000 | 10322000
Asset Condition | 1b | 293 | MA | Eversource |  |  | 2026-06-01 |  | Ludlow 19S 345 kV Full BPS Separation and Asset Condition Project | [16 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | Proposed | NR | No | [16 empty] | 42900000 | 42900000 | 42900000 | 42900000 | 42900000 | 42900000 | 42900000 | 61520000
Asset Condition | 1a | 294 | MA | National Grid, USA |  |  | 2025-08-01 |  | Millbury #2 Substation Protection Scheme Upgrade and Asset Condition Refurbishments | [17 empty] | Planned | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-04-11 | [17 empty] | 28040000 | 28040000 | 28040000 | 28040000 | 28040000 | 28040000 | 28040000
Asset Condition | 1a | 295 | MA | National Grid, USA |  |  | 2022-02-01 |  | C-129N/D-130 115 kV Line Fiber Installation | [17 empty] | Under Construction | In-service | In-service | In-service | In-service | In-service | In-service | NR | 2022-04-11 | [17 empty] | 11220000 | 11220000 | 11220000 | 11220000 | 11220000 | 11220000 | 11220000
Asset Condition | 1a | 296 | MA | National Grid, USA |  |  | 2022-03-01 |  | X-176 115 kV Line Asset Condition Refurbishments | [17 empty] | Planned | Under Construction | In-service | In-service | In-service | In-service | In-service | NR | 2022-04-11 | [17 empty] | 18520000 | 18520000 | 18520000 | 18520000 | 18520000 | 18520000 | 18520000
Asset Condition | 1a | 297 | MA | Eversource |  |  | 2025-12-01 |  | 282-520 & 282-521 115 kV Lines HPFF Refurbishment | [17 empty] | Planned | Planned | Planned | Planned | Planned | Planned | Planned | 2021-08-23 | No | [17 empty] | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000 | 69600000
Asset Condition | 1a | 298 | NH | Eversource |  |  | 2022-06-01 |  | 115 kV Structure and Shield Wire Replacements - Line D121 | [17 empty] | Under Construction | Under Construction | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 13105000 | 13105000 | 13105000 | 13105000 | 13105000 | 13105000 | 13105000
Asset Condition | 1a | 299 | MA | Eversource |  |  | 2021-12-01 |  | 115 kV Structure Replacements - Line 456-522 | [17 empty] | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 5672000 | 5672000 | 5672000 | 5672000 | 5672000 | 5672000 | 5672000
Asset Condition | 1a | 300 | MA | Eversource |  |  | 2021-11-01 |  | 115 kV Structure Replacements - Line 240-510 | [17 empty] | Under Construction | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 11636000 | 11636000 | 11636000 | 11636000 | 11636000 | 11636000 | 11636000
Asset Condition | 1a | 301 | MA | Eversource |  |  | 2021-11-01 |  | 230 kV Structure Replacements - Line 342-603 | [17 empty] | Proposed | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 5451000 | 5451000 | 5451000 | 5451000 | 5451000 | 5451000 | 5451000
Asset Condition | 1a | 302 | CT | Eversource |  |  | 2022-05-01 |  | 690 Line Rebuild and Asset Condition Project | [17 empty] | Proposed | Proposed | Under Construction | In-Service | In-Service | In-service | In-service | 2021-07-15 | 2023-04-28 | [17 empty] | 11000000 | 11000000 | 11045000 | 11045000 | 11045000 | 11045000 | 11045000
Asset Condition | 1a | 303 | CT | Eversource |  |  | 2022-06-01 |  | 115 kV Wood Pole Replacement - Line 1751 | [17 empty] | Proposed | Under Construction | Under Construction | Under Construction | In-Service | In-service | In-service | NR | 2022-12-23 | [17 empty] | 28800000 | 28794000 | 28794000 | 28794000 | 28794000 | 28794000 | 28794000
Asset Condition | 1a | 304 | MA | Eversource |  |  | 2021-04-01 |  | 478-508 & 478-509 115 kV Lines Asset Condition & OPGW | [17 empty] | In-Service | In-Service | In-Service | In-Service | In-Service | In-service | In-service | NR | 2022-05-31 | [17 empty] | 5866000 | 5866000 | 5866000 | 5866000 | 5866000 | 5866000 | 5866000
Asset Condition | 1a | 305 | VT | Vermont Electric Power Company |  |  | 2026-12-01 |  | Line K42 Asset Condition Line Replacement | [18 empty] | Proposed | Planned | Planned | Planned | Planned | Planned | 2022-03-17 | No | [18 empty] | 49000000 | 49000000 | 49000000 | 49000000 | 49000000 | 49000000
Asset Condition | 1a | 306 | MA | National Grid, USA |  |  | 2023-05-01 |  | V-174 115 kV Line Asset Condition Refurbishments and OPGW installation | [18 empty] | Under Construction | Under Construction | Under Construction | Under Construction | In-service | In-service | NR | 2022-10-31 | [18 empty] | 26300000 | 26300000 | 26300000 | 26300000 | 26300000 | 26300000
Asset Condition | 1a | 307 | MA | National Grid, USA |  |  | 2022-05-01 |  | M-139/N-140 115 kV Lines Pilot Protection Schemes | [18 empty] | Under Construction | Under Construction | In-service | In-service | In-service | In-service | NR | 2022-10-31 | [18 empty] | 9400000 | 9400000 | 9400000 | 10560000 | 10560000 | 10560000
Asset Condition | 1a | 308 | NH | National Grid, USA |  |  | 2027-12-01 |  | Moore #20 Substation Asset Condition and Separation | [18 empty] | Proposed | Proposed | Proposed | Planned | Planned | Planned | 2022-12-14 | No | [18 empty] | 49307000 | 49307000 | 49307000 | 49307000 | 49307000 | 49307000
Asset Condition | 1a | 309 | CT | Eversource |  |  | 2023-03-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Glenbrook 115 kV | [18 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | No | [18 empty] | 10034000 | 10034000 | 10034000 | 10034000 | 10034000 | 10034000
Asset Condition | 1a | 310 | CT | Eversource |  |  | 2023-03-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Plumtree 115 kV and 345 kV | [18 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | No | [18 empty] | 19300000 | 19300000 | 19300000 | 19300000 | 19300000 | 19300000
Asset Condition | 1a | 311 | CT | Eversource |  |  | 2023-03-01 |  | Southwest Connecticut (SWCT) Substation Relay Upgrades - Norwalk 115 kV and 345 kV | [18 empty] | Under Construction | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | No | [18 empty] | 16358000 | 16358000 | 16358000 | 16358000 | 16358000 | 16358000
Asset Condition | 1a | 312 | CT | Eversource |  |  | 2023-03-01 |  | Laminated Wood Structure Replacement Program Phase II - 3403 345 kV Line | [18 empty] | Proposed | Proposed | Proposed | Under Construction | In-service | In-service | NR | 2023-06-01 | [18 empty] | 8422000 | 8422000 | 8422000 | 12091000 | 12091000 | 12091000
Asset Condition | 1a | 313 | CT | Eversource |  |  | 2022-04-01 |  | 345 kV Structure and Shield Wire Replacements - 329 Line | [18 empty] | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | NR | 2/7/2023 6/1/2023 | [18 empty] | 6242000 | 6242000 | 6242000 | 6927000 | 6927000 | 6927000
Asset Condition | 1a | 314 | CT | Eversource |  |  | 2022-06-01 |  | 345 kV Structure and Shield Wire Replacements - 352 Line | [18 empty] | Proposed | Under Construction | In-Service | In-Service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5800000 | 5782000 | 5782000 | 5782000 | 5782000 | 5782000
Asset Condition | 1a | 315 | MA | Eversource |  |  | 2023-12-01 |  | 115 kV Structure Replacements and Shield Wire - 191 Line | [18 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2023-02-07 | [18 empty] | 19200000 | 19200000 | 27840000 | 27840000 | 27840000 | 27840000
Asset Condition | 1a | 316 | MA | Eversource |  |  | 2022-12-01 |  | 115 kV Structure Replacements and Shield Wire - 117 Line | [18 empty] | Proposed | Proposed | Proposed | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5900000 | 5880000 | 5880000 | 5880000 | 5880000 | 5880000
Asset Condition | 1a | 317 | MA | Eversource |  |  | 2025-12-11 |  | Edgar Station #150 Brown Glass and Obsolete Equipment Replacement | [18 empty] | Proposed | Proposed | Proposed | Proposed | Under Construction | Under Construction | NR | NR | [18 empty] | 6500000 | 6500000 | 6500000 | 6500000 | 4000000 | 4000000
Asset Condition | 1a | 318 | MA | Eversource |  |  | 2022-06-01 |  | 115 kV Structure Replacements - 211-508 Line | [18 empty] | Proposed | Proposed | In-service | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5800000 | 5800000 | 5800000 | 5800000 | 5800000 | 5800000
Asset Condition | 1a | 319 | MA | Eversource |  |  | 2022-07-01 |  | 115 kV Structure Replacements - 391-508 Line | [18 empty] | Proposed | Proposed | In-service | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Asset Condition | 1a | 320 | MA | Eversource |  |  | 2022-08-01 |  | 115 kV Structure Replacements - 533-508 Line | [18 empty] | Proposed | Proposed | In-service | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 5000000 | 5000000 | 5000000 | 5000000 | 5000000 | 5000000
Asset Condition | 1a | 321 | NH | Eversource |  |  | 2023-04-01 |  | Laminated Wood Structure Replacement Program Phase II - A152 115 kV Line | [18 empty] | Proposed | Under Construction | Under Construction | Under Construction | Under Construction | In-service | NR | 2023-06-01 | [18 empty] | 15264000 | 17476000 | 17476000 | 17476000 | 17476000 | 17476000
Asset Condition | 1a | 322 | NH | Eversource |  |  | 2022-09-01 |  | Laminated Wood Structure Replacement Program Phase II - V191 115 kV Line | [18 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | NR | 2023-06-01 | [18 empty] | 11024000 | 10114000 | 10114000 | 10114000 | 10114000 | 10114000
Asset Condition | 1a | 323 | NH | Eversource |  |  | 2022-12-01 |  | 115 kV Structure and Shield Wire Replacements - T198 Line | [18 empty] | Proposed | Under Construction | Under Construction | In-service | In-service | In-service | NR | 2023-02-07 | [18 empty] | 19100000 | 19113000 | 19113000 | 19113000 | 19113000 | 19113000
Asset Condition | 1a | 324 | NH | Eversource |  |  | 2023-06-01 |  | P145 Line Rebuild - Asset Condition and OPGW | [18 empty] | Proposed | Proposed | Under Construction | Under Construction | Under Construction | In-service | 2022-08-19 | 2023-07-27 | [18 empty] | 52000000 | 52000000 | 52142000 | 52142000 | 52142000 | 52142000
Asset Condition | 1a | 325 | NH | Eversource |  |  | 2022-11-01 |  | Laminated Wood Structure Replacement Program Phase II - R187 115 kV Line | [18 empty] | Proposed | Proposed | Under Construction | In-service | In-service | In-service | NR | 2023-06-01 | [18 empty] | 7541000 | 7541000 | 7541000 | 7541000 | 7541000 | 7541000
Asset Condition | 1a | 326 | NH | Eversource |  |  | 2022-09-01 |  | Laminated Wood Structure Replacement Program Phase II - S188 115 kV Line | [18 empty] | Under Construction | Under Construction | Under Construction | In-service | In-service | In-service | NR | 2023-06-01 | [18 empty] | 7342000 | 7342000 | 7342000 | 7342000 | 7342000 | 7342000
Asset Condition | 1a | 327 | NH | Eversource |  |  | 2022-02-01 |  | Laminated Wood Structure Replacement Program Phase II - M164 115 kV Line | [18 empty] | Under Construction | In-Service | In-Service | In-Service | In-service | In-service | NR | 2023-06-01 | [18 empty] | 6024000 | 6024000 | 6024000 | 6024000 | 6024000 | 6024000
Asset Condition | 1b | 328 | MA | National Grid, USA |  |  | 2026-12-01 |  | Bridgewater #16 Substation Asset Condition Upgrades | [19 empty] | Proposed | Proposed | Proposed | Proposed | Proposed | No | No | [19 empty] | 25950000 | 25950000 | 25950000 | 25950000 | 25950000
Asset Condition | 1a | 329 | MA | Eversource |  |  | 2023-04-01 |  | 115 kV Line Structure and OPGW Replacements - Line 1428 | [19 empty] | Proposed | Proposed | Under Construction | In-service | In-service | 2022-07-20 | 2023-07-26 | [19 empty] | 7994000 | 7994000 | 7994000 | 7994000 | 7994000
Asset Condition | 1a | 330 | VT | Vermont Electric Power Company |  |  | 2026-12-01 |  | Line K21 Asset Condition Structure Refurbishment | [20 empty] | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-23 | [20 empty] | 20550000 | 20550000 | 20550000 | 20550000
Asset Condition | 1a | 331 | VT | Vermont Electric Power Company |  |  | 2026-12-01 |  | Line K32 Asset Condition Structure Refurbishment | [20 empty] | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-22 | [20 empty] | 14320000 | 14320000 | 14320000 | 14320000
Asset Condition | 1a | 332 | VT | Vermont Electric Power Company |  |  | 2027-12-01 |  | Line K50 Asset Condition Structure Refurbishment | [20 empty] | Under Construction | Under Construction | Under Construction | Under Construction | NR | 2022-12-23 | [20 empty] | 31280000 | 31280000 | 31280000 | 31280000
Asset Condition | 1a | 333 | MA | National Grid, USA |  |  | 2025-08-01 |  | Construct new Stafford Street Substation | [20 empty] | Planned | Under Construction | Under Construction | Under Construction | 2020-06-02 | 2023-05-31 | [20 empty] | 56800000 | 56800000 | 56800000 | 56870000
Asset Condition | 1a | 334 | MA | National Grid, USA |  |  | 2023-05-01 |  | K-137/L-138W 115 kV Lines Pilot Protection Scheme | [20 empty] | Planned | Under Construction | In-service | In-service | NR | 2023-02-07 | [20 empty] | 19940000 | 19940000 | 20540000 | 20540000
Asset Condition | 1a | 335 | RI | Rhode Island Energy |  |  | 2024-12-01 |  | G-185S/L-190 115 kV OPGW Installation from Davisville Tap to West Kingston (L-190 to Wickford Junction) | [20 empty] | Planned | Under Construction | Under Construction | Under Construction | NR | No | [20 empty] | 8493000 | 8493000 | 8493000 | 8493000
Asset Condition | 1b | 336 | MA | National Grid, USA |  |  | 2027-05-01 |  | Tewksbury #22 Substation Asset Condition Replacements | [20 empty] | Proposed | Proposed | Proposed | Proposed | No | No | [20 empty] | 35490000 | 35490000 | 35490000 | 35490000
Asset Condition | 1b | 337 | MA | National Grid, USA |  |  | 2030-12-01 |  | E-5/F-6 69kV Line Asset Condition Refurbishments | [20 empty] | Concept | Concept | Concept | Concept | 2022-07-11 | No
Asset Condition | 1b | 338 | CT | Eversource |  |  | 2026-06-01 |  | Millstone Substation 345 kV Breaker Replacements | [20 empty] | Proposed | Proposed | Proposed | Proposed | NR | No | [20 empty] | 17600000 | 17600000 | 17600000 | 17600000
Asset Condition | 1a | 339 | MA | Eversource |  |  | 2024-03-01 |  | Northfield Mountain Substation 345 kV Breaker Replacements | [20 empty] | Proposed | Proposed | Proposed | Under Construction | NR | No | [20 empty] | 9200000 | 9200000 | 9200000 | 9005000
Asset Condition | 1a | 340 | MA | Eversource |  |  | 2023-12-01 |  | Holbrook Station 345/115 kV Autotransformer Replacement | [20 empty] | Proposed | Under Construction | Under Construction | Under Construction | 2022-09-22 | No | [20 empty] | 10290000 | 10155000 | 10155000 | 10155000
Asset Condition | 1a | 341 | NH | Eversource |  |  | 2023-06-01 |  | Deerfield Station 345 kV Breaker Replacements | [20 empty] | Under Construction | Under Construction | Under Construction | In-service | NR | No | [20 empty] | 5182000 | 5182000 | 5182000 | 5182000
Asset Condition | 1a | 342 | NH | Eversource |  |  | 2022-11-01 |  | Line 379 Asset Condition Wood Structure Replacements | [20 empty] | Under Construction | In-service | In-service | In-service | NR | No | [20 empty] | 8020000 | 8020000 | 8020000 | 8020000
Asset Condition | 1a | 343 | NH | Eversource |  |  | 2024-06-01 |  | Timber Swamp Station 345 kV Breaker Replacements | [20 empty] | Proposed | Under Construction | Under Construction | Under Construction | NR | No | [20 empty] | 7431000 | 7431000 | 7431000 | 7431000
Asset Condition | 1a | 344 | NH | Eversource |  |  | 2023-02-01 |  | Line 373 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | In-service | In-service | NR | No | [20 empty] | 7066000 | 7066000 | 7066000 | 7066000
Asset Condition | 1a | 345 | NH | Eversource |  |  | 2023-03-01 |  | Line 326 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | In-service | In-service | NR | No | [20 empty] | 6194000 | 6194000 | 6194000 | 6194000
Asset Condition | 1a | 346 | NH | Eversource |  |  | 2023-02-01 |  | Line 385 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | In-service | In-service | NR | No | [20 empty] | 5035000 | 5035000 | 5035000 | 5035000
Asset Condition | 1a | 347 | NH | Eversource |  |  | 2023-02-01 |  | Line 391 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | In-service | In-service | NR | No | [20 empty] | 8953000 | 8953000 | 8953000 | 8953000
Asset Condition | 1a | 348 | NH | Eversource |  |  | 2023-06-01 |  | Line C196 Asset Condition Wood Structure Replacements | [20 empty] | Proposed | Under Construction | Under Construction | In-service | NR | No | [20 empty] | 14800000 | 14800000 | 11690000 | 11690000
Asset Condition | 1a | 349 | NH | Eversource |  |  | 2025-06-01 |  | Scobie Pond Station 345 kV Trench Replacement & Control House Expansion Project | [20 empty] | Proposed | Under Construction | Under Construction | Under Construction | NR | 2023-04-25 | [20 empty] | 19652000 | 19652000 | 19652000 | 19652000
Asset Condition | 1a | 350 | VT | Vermont Electric Power Company |  |  | 2024-12-01 |  | Middlebury Substation Asset Condition Refurbishment | [21 empty] | Planned | Planned | Under Construction | NR | No | [21 empty] | 9000000 | 9000000 | 9000000
Asset Condition | 1a | 351 | NH | Eversource |  |  | 2024-12-01 |  | Greggs Substation Rebuild | [21 empty] | Under Construction | Under Construction | Under Construction | 2022-11-16 | 2023-09-12 | [21 empty] | 72193000 | 72193000 | 72193000
Asset Condition | 1a | 352 | CT | Eversource |  |  | 2025-06-01 |  | Trumbull - Norwalk Corridor Partial 115 kV Line Rebuilds - 1637/1720 and 1714/1720/1222 Lines | [21 empty] | Proposed | Proposed | Under Construction | 2023-01-19 | No | [21 empty] | 159590000 | 159590000 | 159590000
Asset Condition | 1a | 353 | MA | National Grid, USA |  |  | 2022-11-01 |  | 326 345 kV Line Structure Replacements | [21 empty] | Under Construction | In-service | In-service | NR | No | [21 empty] | 8900000 | 8900000 | 8900000
Asset Condition | 1b | 354 | MA | National Grid, USA |  |  | 2025-08-01 |  | Maplewood #16 Substation Asset Replacements | [21 empty] | Proposed | Proposed | Proposed | NR | 2023-09-12 | [21 empty] | 6170000 | 6170000 | 6170000
Asset Condition | 1a | 355 | CT | Eversource |  |  | 2023-04-01 |  | 115 kV Structure Replacements and OPGW Installation - 1783 Line | [21 empty] | Under Construction | Under Construction | In-service | NR | 2023-07-27 | [21 empty] | 6285000 | 6285000 | 6285000
Asset Condition | 1b | 356 | CT | Eversource |  |  | 2024-06-01 |  | 115 kV Line Asset Condition and OPGW Project - Line 348 | [21 empty] | Proposed | Proposed | Proposed | No | No | [21 empty] | 8400000 | 8400000 | 8400000
Asset Condition | 1a | 357 | CT | Eversource |  |  | 2024-06-01 |  | 115 kV Line Asset Condition and OPGW Project - Line 1772 | [21 empty] | Under Construction | Under Construction | Under Construction | NR | No | [21 empty] | 20730000 | 20730000 | 20730000
Asset Condition | 1b | 358 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Structure Replacements and OPGW Installation - 3041 Line | [21 empty] | Proposed | Proposed | Proposed | NR | No | [21 empty] | 11600000 | 11600000 | 11600000
Asset Condition | 1a | 359 | CT | Eversource |  |  | 2024-06-01 |  | 345 kV Structure Replacements and OPGW Installation - 362 Line | [21 empty] | Under Construction | Under Construction | Under Construction | NR | No | [21 empty] | 19163000 | 19163000 | 19163000
Asset Condition | 1a | 360 | CT | Eversource |  |  | 2024-06-01 |  | East Devon 345/115 kV Relay Upgrades | [21 empty] | Under Construction | Under Construction | Under Construction | NR | No | [21 empty] | 6720000 | 6720000 | 6720000
Asset Condition | 1a | 361 | CT | Eversource |  |  | 2023-12-01 |  | 115kV Lattice Tower and Shield Wire Replacements - 1261/1598 Line | [21 empty] | Proposed | Proposed | Under Construction | NR | No | [21 empty] | 5600000 | 5600000 | 7273000
Asset Condition | 1b | 362 | CT | Eversource |  |  | 2024-06-01 |  | 115kV Lattice Tower, Shield Wire, and Conductor Replacements - 1355/1610 Line | [21 empty] | Proposed | Proposed | Proposed | No | No | [21 empty] | 50400000 | 50400000 | 50400000
Asset Condition | 1b | 363 | CT | Eversource |  |  | 2024-03-01 |  | Asset Condition Wood Structure Replacements - 1208 115 kV Line | [21 empty] | Proposed | Proposed | Proposed | NR | No | [21 empty] | 5842000 | 5842000 | 5842000
Asset Condition | 1a | 364 | MA | Eversource |  |  | 2024-06-01 |  | High Hill Station 644 Control House Replacement | [21 empty] | Planned | Planned | Under Construction | NR | No | [21 empty] | 19270000 | 19270000 | 19270000
Asset Condition | 1a | 365 | MA | Eversource |  |  | 2024-03-01 |  | Asset Condition Wood Structure Replacements - 389 345 kV Line | [21 empty] | Planned | Planned | Under Construction | NR | No | [21 empty] | 6648000 | 6648000 | 6648000
Asset Condition | 1a | 366 | NH | Eversource |  |  | 2023-02-01 |  | Eagle Substation 345/115 kV Autotransformer Replacement | [21 empty] | Under Construction | In-service | In-service | 2022-09-22 | 2023-04-28 | [21 empty] | 6375000 | 6375000 | 6375000
Asset Condition | 1a | 367 | NH | Eversource |  |  | 2023-12-01 |  | 115 kV Structure Replacements and OPGW Installation - P106 Line | [21 empty] | Under Construction | Under Construction | Under Construction | NR | 2023-07-27 | [21 empty] | 5634000 | 5634000 | 5634000
Asset Condition | 1a | 368 | NH | Eversource |  |  | 2023-11-01 |  | 115 kV Structure Replacements and OPGW Installation - Q171 Line | [21 empty] | Under Construction | Under Construction | Under Construction | NR | 2023-07-27 | [21 empty] | 14966000 | 14966000 | 14966000
Asset Condition | 1a | 369 | NH | Eversource |  |  | 2023-08-01 |  | Asset Condition Wood Structure Replacements - C196 115 kV Line | [21 empty] | Proposed | Proposed | In-service | NR | No | [21 empty] | 6191000 | 6191000 | 6191000
Asset Condition | 1a | 370 | NH | Eversource |  |  | 2024-03-01 |  | Line 381/379 Optical Ground Wire Upgrade | [21 empty] | Under Construction | Under Construction | Under Construction | NR | No | [21 empty] | 8238000 | 8238000 | 8238000
Asset Condition | 1a | 371 | CT | Eversource |  |  | 2023-12-01 |  | South Naugatuck to Devon Rebuild - Segment 1 (Stevenson substation - Pootatuck substation) | [22 empty] | Under Construction | Under Construction | 2023-09-20 | No | [22 empty] | 87289000 | 87289000
Asset Condition | 1b | 372 | CT | Eversource |  |  | 2025-12-01 |  | South Naugatuck to Devon Rebuild - Segment 2 (Pootatuck substation - West Devon Jct.) | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 46090000 | 46090000
Asset Condition | 1b | 373 | CT | Eversource |  |  | 2025-12-01 |  | South Naugatuck to Devon Rebuild - Segment 3 (West Devon Jct. - Devon substation) | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 41110000 | 41110000
Asset Condition | 1b | 374 | CT | Eversource |  |  | 2025-12-01 |  | South Naugatuck to Devon Rebuild - Segment 4 (Christian Street Jct. - Stevenson substation) | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 52960000 | 52960000
Asset Condition | 1b | 375 | CT | Eversource |  |  | 2025-12-01 |  | South Naugatuck to Devon Rebuild - Segment 5 (Towantic substation - South Naugatuck substation) | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 115100000 | 115100000
Asset Condition | 1a | 376 | CT | Eversource |  |  | 2025-12-01 |  | CT Asset Condition Project - Card to Montville Corridor (Reconductor/OPGW lines 1000 and 1090, OPGW lines 1070, 1080, 1490) | [22 empty] | Under Construction | Under Construction | No | No | [22 empty] | 37198000 | 37198000
Asset Condition | 1b | 377 | CT | Eversource |  |  | 2024-06-01 |  | CT Asset Condition Project - Line 376 | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 9020000 | 9020000
Asset Condition | 1a | 378 | CT | Eversource |  |  | 2024-03-01 |  | CT Asset Condition Project - Line 1620 | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 8821000 | 8821000
Asset Condition | 1b | 379 | CT | Eversource |  |  | 2024-03-01 |  | CT Asset Condition Project - Lines 1132 and 1505 | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 13383000 | 13383000
Asset Condition | 1a | 380 | NH | Eversource |  |  | 2023-12-01 |  | NH Asset Condition Project - H123 Line | [22 empty] | Under Construction | Under Construction | NR | No | [22 empty] | 5800000 | 5800000
Asset Condition | 1a | 381 | NH | Eversource |  |  | 2023-05-01 |  | NH Asset Condition Project - M183 Line | [22 empty] | Under Construction | In-service | NR | No | [22 empty] | 6000000 | 6000000
Asset Condition | 1b | 382 | NH | Eversource |  |  | 2025-03-01 |  | NH Asset Condition Project - F139 Line | [22 empty] | Proposed | Proposed | 2023-09-20 | No | [22 empty] | 58000000 | 46628000
Asset Condition | 1a | 383 | VT | Vermont Electric Power Company |  |  | 2026-12-01 |  | Line K43 Asset Condition Structure Refurbishment | [22 empty] | Planned | Under Construction | NR | No | [22 empty] | 16900000 | 16900000
Asset Condition | 1b | 384 | MA | National Grid, USA |  |  | 2028-08-01 |  | Shutesbury #704 Substation Rebuild | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 8900000 | 8900000
Asset Condition | 1b | 385 | MA | National Grid, USA |  |  | 2027-10-01 |  | E-131 Asset Condition Refurbishment | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 138300000 | 138300000
Asset Condition | 1a | 386 | NH | Eversource |  |  | 2024-12-01 |  | Northern New Hampshire 115kV Line Rebuilds - B112 Line | [22 empty] | Proposed | Under Construction | 2023-06-14 | No | [22 empty] | 105430000 | 105432000
Asset Condition | 1b | 387 | NH | Eversource |  |  | 2026-12-01 |  | Northern New Hampshire 115kV Line Rebuilds - Q195 Line | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 100000000 | 100000000
Asset Condition | 1b | 388 | NH | Eversource |  |  | 2026-06-01 |  | Northern New Hampshire 115kV Line Rebuilds - U199 Line | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 51180000 | 51180000
Asset Condition | 1b | 389 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - 391 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 12370000 | 12370000
Asset Condition | 1b | 390 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - 373 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 10280000 | 10280000
Asset Condition | 1b | 391 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - R193 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 7700000 | 7700000
Asset Condition | 1b | 392 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - S153 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 5000000 | 5000000
Asset Condition | 1b | 393 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - A126 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 8370000 | 8370000
Asset Condition | 1a | 394 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - E194 Line | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 8670000 | 8670000
Asset Condition | 1a | 395 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - U181 Line | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 8510000 | 8510000
Asset Condition | 1b | 396 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - D121 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 5000000 | 5036000
Asset Condition | 1a | 397 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - 307 Line | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 9420000 | 9417000
Asset Condition | 1b | 398 | NH | Eversource |  |  | 2024-03-01 |  | NH Wood Structure Replacements and OPGW Installation - B143 Line | [22 empty] | Proposed | Proposed | NR | No | [22 empty] | 17280000 | 17275000
Asset Condition | 1a | 399 | NH | Eversource |  |  | 2023-12-01 |  | NH Wood Structure Replacements and OPGW Installation - J114 Line | [22 empty] | Proposed | Under Construction | NR | No | [22 empty] | 9710000 | 9709000
Asset Condition | 1b | 400 | MA | National Grid, USA |  |  | 2030-03-31 |  | Adams #21 Substation Relocation | [22 empty] | Proposed | Proposed | No | No | [22 empty] | 55100000 | 55100000
Asset Condition | 1a | 401 | NH | Eversource |  |  | 2024-03-01 |  | Laminated Wood Structure Replacement Program Phase III - C189 | [23 empty] | Under Construction | NR | No | [23 empty] | 12808000
Asset Condition | 1a | 402 | NH | Eversource |  |  | 2024-03-01 |  | Laminated Wood Structure Replacement Program Phase III - H137 | [23 empty] | Under Construction | NR | No | [23 empty] | 7788000
Asset Condition | 1b | 403 | NH | Eversource |  |  | 2024-03-01 |  | Laminated Wood Structure Replacement Program Phase III - M108 | [23 empty] | Proposed | NR | No | [23 empty] | 13399000
Asset Condition | 1b | 404 | NH | Eversource |  |  | 2024-12-01 |  | Laminated Wood Structure Replacement Program Phase III - V182 | [23 empty] | Proposed | NR | No | [23 empty] | 32915000
Asset Condition | 1a | 405 | NH | Eversource |  |  | 2024-03-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - H141 | [23 empty] | Under Construction | NR | No | [23 empty] | 18750000
Asset Condition | 1b | 406 | NH | Eversource |  |  | 2025-09-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - A164 | [23 empty] | Proposed | NR | No | [23 empty] | 66960000
Asset Condition | 1b | 407 | NH | Eversource |  |  | 2024-09-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - R169 | [23 empty] | Proposed | NR | No | [23 empty] | 8400000
Asset Condition | 1b | 408 | NH | Eversource |  |  | 2024-12-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - F162 | [23 empty] | Proposed | NR | No | [23 empty] | 21840000
Asset Condition | 1b | 409 | NH | Eversource |  |  | 2025-03-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - G146 | [23 empty] | Proposed | NR | No | [23 empty] | 58380000
Asset Condition | 1b | 410 | NH | Eversource |  |  | 2024-09-01 |  | Laminated Wood Structure Replacement Program Phase III and OPGW - I158 | [23 empty] | Proposed | NR | No | [23 empty] | 28630000
Asset Condition | 1b | 411 | NH | Eversource |  |  | 2025-06-01 |  | Deerfield 345/115 kV Relay Upgrades | [23 empty] | Proposed | NR | No | [23 empty] | 5820000
Asset Condition | 1b | 412 | CT | Eversource |  |  | 2026-12-01 |  | 1704 Underground Cable Rebuild Project | [23 empty] | Proposed | No | No | [23 empty] | 169300000
Asset Condition | 1b | 413 | CT | Eversource |  |  | 2024-09-01 |  | Structure Replacements & OPGW Installations - 364 Line | [23 empty] | Proposed | NR | No | [23 empty] | 12610000
Asset Condition | 1b | 414 | CT | Eversource |  |  | 2024-09-01 |  | Structure Replacements & OPGW Installations - 348 Line | [23 empty] | Proposed | NR | No | [23 empty] | 9700000
Asset Condition | 1b | 415 | CT | Eversource |  |  | 2025-03-01 |  | Structure Replacements & OPGW Installations - 1726 Line | [23 empty] | Proposed | NR | No | [23 empty] | 8863000
Asset Condition | 1b | 416 | CT | Eversource |  |  | 2024-12-01 |  | Southington 115 kV Relay Upgrades | [23 empty] | Proposed | NR | No | [23 empty] | 13850000
Asset Condition | 1a | 417 | MA | National Grid, USA |  |  | 2024-07-01 |  | Northboro Road Substation Breaker Replacements | [23 empty] | Under Construction | NR | No | [23 empty] | 5230000
Asset Condition | 1b | 418 | MA | National Grid, USA |  |  | 2024-07-01 |  | 308 345 kV Line Asset Condition Refurbishment | [23 empty] | Proposed | NR | No | [23 empty] | 15770000
Asset Condition | 1b | 419 | MA | National Grid, USA |  |  | 2026-07-01 |  | S8 115 kV Line Asset Condition Project | [23 empty] | Proposed | No | No | [23 empty] | 88240000
Asset Condition | 1b | 420 | MA | National Grid, USA |  |  | 2029-03-01 |  | V5/U6 115 kV Line Asset Condition Project | [23 empty] | Proposed | No | No | [23 empty] | 131980000
Asset Condition | 1b | 421 | MA | Eversource |  |  | 2025-12-01 |  | NERC CIP-014 - Physical Security Upgrades - Round 1 | [23 empty] | Under Construction | No | No | [23 empty] | 121092000
Asset Condition | 1a | 422 | CT | Eversource |  |  | 2020-12-01 |  | NERC CIP-014 - Physical Security Upgrades - Round 1 | [23 empty] | In-service | No | No | [23 empty] | 53527000
Asset Condition | 1b | 423 | CT | Eversource |  |  | 2026-12-01 |  | 1722 Underground Cable Rebuild Project | [23 empty] | Proposed | No | No | [23 empty] | 132300000